## Зведена таблиця
List of equipment damaged during air strikes and needed to be replaced
Company | Infrastructure | Name of branch | Equipment | Unit | Quantity | Estimated total value (Euros, excl. VAT) | Lost/installed capacity | Priority of restoration | Deadline for supply of equipment to ensure performance of the assignments | Recovery date (if the equipment is delivered on the specified date) | Possible manufacturer | Impact | Comments | Status of covering the need for equipment | Status of covering the need for equipment | Power unit number
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Tsentrenergo | Generation | Zmiivska TPP | Generator ТГВ 200 M | pcs. | 2 | 20000000 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 1 | 2024 | December 2024 | JSC "Zavod Elektrovazhmash", Siemens | Restoration of power unit operation capability |  | It is planned to receive humanitarian aid from a donor in the Republic of Lithuania (with the assistance of European Commission Directorate-General for European Civil Protection and Humanitarian Aid Operations (ECHO)) | yes | block 5, 6
Tsentrenergo | Generation | Zmiivska TPP | Autotype transformer АТДЦТН-200000/330/110-74У | pcs. | 3 | 8596200 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 1 | 2024 | December 2024 | ZRT (Zaporizhia transformer), Hitachi, Siemens, ABB | restoration of the design scheme of the distribution device of the Zmiyiv TPP to provide electricity to consumers in the Kharkiv region |  | * The purchase of ATDCTN-200000 - 2 pcs. is carried out within the framework of support from USAID * It is planned to receive ATDCTN-200000 -1pcs., as humanitarian aid from a donor in the Republic of Lithuania (with the assistance of European Commission Directorate-General for European Civil Protection and Humanitarian Aid Operations (ECHO)) | yes | open switchgear-330kV
Tsentrenergo | Generation | Zmiivska TPP | Transformer [circuit-breaker] fluid Shell Diala S4 ZX-1 | t | 200 | 501600 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 1 | 2024 | December 2024 | According to the results of bidding. | restoration of the design scheme of the distribution device of the Zmiyiv TPP to provide electricity to consumers in the Kharkiv region |  | Procurement is carried out within the framework of support from USAID | yes | for filling oil-filled electrical equipment
Tsentrenergo | Generation | Zmiivska TPP | Current transformer 110 kV | pcs. | 6 | 58140 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 1 | 2024 | December 2024 | ABB, Siemens, Koncar | restoration of the design scheme of the distribution device of the Zmiyiv TPP to provide electricity to consumers in the Kharkiv region |  | Procurement is carried out within the framework of support from USAID | yes | open switchgear
Tsentrenergo | Generation | Zmiivska TPP | Сircuit breaker 110kV type LTD-145D1/B | pcs. | 3 | 115275 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 1 | 2024 | December 2024 | ABB, Siemens, Koncar, Hitachi | restoration of the design scheme of the distribution device of the Zmiyiv TPP to provide electricity to consumers in the Kharkiv region |  | Procurement is carried out within the framework of support from USAID | yes | open switchgear
Tsentrenergo | Generation | Zmiivska TPP | Current transformer 330 kV ТОМ-362 ІІ U-0,2S/0,2S/0,2S/5P/5P/5Р-1000-2000/1 У1 or equivalent | pcs. | 4 | 59232 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 1 | 2024 | December 2024 | ABB, Siemens, Hitachi | restoration of the design scheme of the distribution device of the Zmiyiv TPP to provide electricity to consumers in the Kharkiv region |  | Procurement is carried out within the framework of support from USAID | yes | open switchgear
Tsentrenergo | Generation | Zmiivska TPP | Overvoltage suppressor 330 kW PEXLIM P 276-XH 362, Set of 3 phases | pcs. | 1 | 7650 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 1 | 2024 | December 2024 | ABB, Siemens, Hitachi | restoration of the design scheme of the distribution device of the Zmiyiv TPP to provide electricity to consumers in the Kharkiv region |  | Procurement is carried out within the framework of support from USAID | yes | avtotransformer AT-А
Tsentrenergo | Generation | Zmiivska TPP | shut-off and regulating valves of high and medium pressure in an assortment for boiler and turbine equipment | set | 1 | 2350 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 1 | 2024 | December 2024 | Ukrainian manufacturer: PJSC "PRMZ", PE PLMZ, PJSC Nikopol Pipe Fitting Plant | ensuring reliability and maneuverability during start-up operations and shutdowns (including emergency) of power units, with optimization of time for inclusion in the network. |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Cable products | m | 50000 | 500000 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 1 | 2024 | December 2024 | Zaporizhzhia Cable Plant, Odesa Cable Plant | For power supply and switching of damaged equipment |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 5,6
Tsentrenergo | Generation | Zmiivska TPP | Generator ТГВ-200 | pcs | 2 | 20000000 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 2 | 01.04.2025 | June 2025 | JSC "Zavod Elektrovazhmash", Siemens | Restoration of power unit operation capability |  |  | no | block 2,3
Tsentrenergo | Generation | Zmiivska TPP | Transformer bushing 110 kV | pcs | 3 | 76338 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 2 | 01.04.2025 |  | ABB, Siemens, Hitachi | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | open switchgear
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 1500 rpm, 200 kW | pcs | 2 | 15300 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.04.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 1500 rpm, 160 kW | pcs | 2 | 15300 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.04.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 1500 rpm, 21 kW | pcs | 2 | 1526 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.09.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 1500 rpm, 11 kW | pcs | 3 | 1437 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.09.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 750 rpm, 28 kW | pcs | 2 | 3644 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.09.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 2985 rpm, 4000 kW | pcs | 1 | 417500 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.09.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 2985 rpm, 3800 kW | pcs | 2 | 835000 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.09.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 1500 rpm, 18,51 kW | pcs | 6 | 4578 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.09.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 1500 rpm, 20 kW | pcs | 2 | 1526 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.09.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Zmiivska TPP | Electric motor 375 rpm, 1700 kW | pcs | 1 | 417500 | Decreasing the reliability of electric networks in the Kharkiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kharkiv region | 3 | 01.09.2025 | December 2025 | According to the results of open bidding. Siemens, Helmke, Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | Procurement is carried out in accordance with the Request for Support dated 03.28.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine | yes | block 1-6
Tsentrenergo | Generation | Trypilska TPP | Generator ТГВ-300 | pcs | 1 | 12000000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | JSC "Zavod Elektrovazhmash", Siemens | to replace damaged power plant equipment in order to stabilize the operation of TPP generating equipment in UES of Ukraine. |  |  | no | block 4
Tsentrenergo | Generation | Trypilska TPP | Brush ring apparatus | pcs | 4 | 288960 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | JSC "Zavod Elektrovazhmash", Siemens |  |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 1,3,4,6
Tsentrenergo | Generation | Trypilska TPP | Cable products | m | 80000 | 800000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | Zaporizhzhia Cable Plant, Odesa Cable Plant | For power supply and switching of damaged equipment |  | Procurement is carried out within the framework of support from USAID | yes | block 4,5
Tsentrenergo | Generation | Trypilska TPP | Block transformer ТДЦ-400000/330 | pcs | 2 | 11295000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | ZRT (Zaporizhia transformer),ABB, Hitachi, Siemens | to replace damaged power plant equipment in order to stabilize the operation of TPP generating equipment in UES of Ukraine. |  | Procurement is carried out within the framework of support from USAID | yes | block 3, 4
Tsentrenergo | Generation | Trypilska TPP | Transformer for own needs ТРДНС-32000/20/6/6 | pcs | 1 | 492400 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | ZRT (Zaporizhia transformer),ABB, Hitachi, Siemens | to replace damaged power plant equipment in order to stabilize the operation of TPP generating equipment in UES of Ukraine. |  | Procurement is carried out within the framework of support from USAID | yes | block 4
Tsentrenergo | Generation | Trypilska TPP | Autotype transformer АТДЦТН-125000/330/110-77У1 330kW | pcs | 1 | 1568750 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 2 | 01.04.2025 | June 2025 | ZRT (Zaporizhia transformer),ABB, Hitachi, Siemens | to replace damaged power plant equipment in order to stabilize the operation of TPP generating equipment in UES of Ukraine. |  |  | no | open switchgear-330kV
Tsentrenergo | Generation | Trypilska TPP | Transformer oil | t | 200 | 501600 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | According to the results of bidding. | to replace damaged power plant equipment in order to stabilize the operation of TPP generating equipment in UES of Ukraine. |  | Procurement is carried out within the framework of support from USAID | yes | for filling oil-filled electrical equipment
Tsentrenergo | Generation | Trypilska TPP | Oil TP-22s | t | 300 | 630000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | According to the results of bidding. | to replace damaged power plant equipment in order to stabilize the operation of TPP generating equipment in UES of Ukraine. |  | Procurement is carried out within the framework of support from USAID | yes | for filling oil tanks on blocks 1-6
Tsentrenergo | Generation | Trypilska TPP | shut-off and regulating valves of high and medium pressure in an assortment for boiler and turbine equipment | set | 1 | 2350000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | Ukrainian manufacturer: PJSC "PRMZ", PE PLMZ, PJSC Nikopol Pipe Fitting Plant | ensuring reliability and maneuverability during start-up operations and shutdowns (including emergency) of power units, with optimization of time for inclusion in the network. |  | Part of the procurement (1087900 euro) is carried out in accordance with the Request for Support dated 04.04.24 with changes, which was approved by the Working Group of the Ministry of Energy of Ukraine. | no | block 3,4
Tsentrenergo | Generation | Trypilska TPP | Turbine section covering | m2 | 21600 | 367200 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | Kyiv plant of roofing materials | protection of main and auxiliary equipment from atmospheric effects |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | the main building
Tsentrenergo | Generation | Trypilska TPP | corrugated board for closing window openings permanent, temporary ends rows A, Б, В, Г | m2 | 5300 | 47700 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | Kyiv plant of roofing materials | protection of main and auxiliary equipment from atmospheric effects |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | the main building
Tsentrenergo | Generation | Trypilska TPP | Feeding electric pump unit ПЕ 600-300 | pcs | 2 | 3000000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 1 | 2024 | December 2024 | PE PLMZ | ensuring reliability and maneuverability during start-up operations and shutdowns (including emergency) of power units, with optimization of the time for inclusion in the network and stable operation of the power unit. |  | Procurement is carried out within the framework of support from USAID | yes | block 3,4
Tsentrenergo | Generation | Trypilska TPP | Generator ТГВ-300 | pcs | 2 | 24000000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 2 | 01.04.2025 | June 2025 | JSC "Zavod Elektrovazhmash", Siemens | to replace damaged power plant equipment in order to stabilize the operation of TPP generating equipment in UES of Ukraine. |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 3,6
Tsentrenergo | Generation | Trypilska TPP | Turbocharger pump unit ОСПТ-1150 | pcs | 2 | 3000000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 2 | 01.04.2025 | June 2025 | PE PLMZ, JSC Ukrainian Energy Machines | ensuring reliability and maneuverability during start-up operations and shutdowns (including emergency) of power units, with optimization of the time for inclusion in the network and stable operation of the power unit. |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 4, 5
Tsentrenergo | Generation | Trypilska TPP | Turbine oil pump | pcs | 4 | 56000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 2 | 01.04.2025 | June 2025 | Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 3,4
Tsentrenergo | Generation | Trypilska TPP | Emergency turbine oil pump | pcs | 4 | 3600 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 2 | 01.04.2025 | June 2025 | Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 3,4
Tsentrenergo | Generation | Trypilska TPP | Increased turbine oil pump | pcs | 4 | 3052 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 2 | 01.04.2025 | June 2025 | Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 3,4
Tsentrenergo | Generation | Trypilska TPP | Emergency oil pump, reinforced turbineт | pcs | 2 | 1526 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 2 | 01.04.2025 | June 2025 | Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 3,4
Tsentrenergo | Generation | Trypilska TPP | Gas cooling pump | pcs | 4 | 56000 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 2 | 01.04.2025 | June 2025 | Slobodian Electromechanical Plant | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 3,4
Tsentrenergo | Generation | Trypilska TPP | Brush ring apparatus | pcs | 2 | 144480 | Decreasing the reliability of electric networks in the Kyiv region, emergency state of auxiliary equipment of power units, decrease in the reliability of electricity production for the Kyiv region | 2 | 01.04.2025 | June 2025 | JSC "Zavod Elektrovazhmash", Siemens | restoration of this equipment ensures the operability of the main equipment and the power unit as a whole |  | The Ministry of Energy of Ukraine has developed a new form for processing Requests for support to Framework Agreements. Accordingly, relevant Support Requests are currently being prepared. | no | block 2,5
KHARKIV CHPP-5 | СHP | Unit 3 | Electric pump unit type D1600-90. Pumps: NTV-3A; NTV-3B | pcs | 1 | 12500 |  | 1 | 2nd quarter of 2024 | 10 days from the date of delivery of the equipment |  | The need to restore generating capacities to ensure the operation of the power grid, improve the reliability of power supply to consumers of the Kharkiv power node, and reduce the scope of consumer restrictions in repair and possible post-emergency modes. | the exact term of the works will depend on the number and duration of air alarms | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 1,2 | Main ejector of turbine generators TG-1, 2 of type EP-3-2A | pcs | 2 | 60000 | 240/240 MW | 1 | 2nd quarter of 2024 | 14 days from the date of delivery of the equipment |  | The need to restore generating capacities to ensure the operation of the power grid, improve the reliability of power supply to consumers of the Kharkiv power node, and reduce the scope of consumer restrictions in repair and possible post-emergency modes. |  | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 3 | Gate valve DN800, Pu25 | pcs | 3 | 60000 |  | 1 | 2nd quarter of 2024 | 5 days from the date of delivery of the equipment |  | The need to restore generating capacities to ensure the operation of the power grid, improve the reliability of power supply to consumers of the Kharkiv power node, and reduce the scope of consumer restrictions in repair and possible post-emergency modes. |  | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Набір для відновлення системи автоматичного керування турбіни Т-110/120-130-4. | встановити | 1 | 92350 | 120/120 МВт | 1 | 4 квартал 2024 року | 5 днів з моменту постачання обладнання |  | Необхідність відновлення системи керування турбіною на енергоблоці . Технологічне обладнання. Потрібен комплексний інженерний проект. | Без автоматичної системи керування турбіною Т-110/120-130-4 неможлива робота енергоблоку | заявка подана, торгів немає | no | Block X
KHARKIV CHPP-5 | СHP | Unit 1,2,3 | Technological videographic recorders. | pcs | 23 | 33810 |  | 1 | 2nd quarter of 2024 | 5 days from the date of delivery of the equipment |  | The need to restore registration and visual control of changes in process parameters and provide relay outputs of feed electric pumps of units 1, 2, 3 |  | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Привід електричний однообертовий МЕО250/25-0,25У-99К з механічним гальмом і джерелом живлення. | шт | 1 | 1800 | 120/120 МВт | 1 | 4 квартал 2024 року | 5 днів з моменту постачання обладнання |  | Необхідність відновлення працездатності технологічного обладнання енергоблоку . Потрібен комплексний інженерний проект. |  | заявка подана, торгів немає | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Braun E1623.11D U2 M measuring rotation speed converter with indication for VOITH hydraulic coupling. | pcs | 2 | 2400 | 120/120 MW | 1 | 4nd quarter of 2024 | 2 days from the date of delivery of the equipment |  | Necessity to restore the performance of power unit No.2 |  | request submitted, no bidding | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Contrac RHD 250-10/EBN 853 electric control lever actuator for VOITH hydraulic coupling | pcs | 1 | 8000 | 120/120 MW | 2 | 4nd quarter of 2024 | 2 days from the date of delivery of the equipment |  | Necessity to restore the performance of power unit No.2 |  | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Automatic gas analysers of hydrogen purity | set | 3 | 33000 | 120/120 MW | 1 | 4nd quarter of 2024 | 7 days from the date of delivery of the equipment |  | Necessity to restore the performance of power unit No.2 | Commissioning and safe operation of the turbogenerator is impossible without complete restoration of the chemical control equipment | request submitted, no bidding | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | A set of spare parts and materials for the restoration of local control panels for the turbine generator, high-pressure preheater, low-pressure preheater and evaporator plant of turbine Т-110/120-130-4 | set | 1 | 91000 | 120/120 MW | 1 | 4nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | Necessity to restore the performance of power unit No.2 | Without full restoration of the local shields of the turbogenerator, high-pressure heater, low-pressure heater and of the T-110/120-130-4 turbine evaporation plant, operation of power unit No. 2 is impossible | request submitted, no bidding | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | A device for continuous measurement of hydrogen ion activity (pH) and temperature (ºС) of water solutions, as well as the emf (mV) of pH electrodes in the steam-water path. | set | 1 | 12000 | 120/120 MW | 1 | 4nd quarter of 2024 | 2 days from the date of delivery of the equipment |  | Necessity to restore the performance of power unit No.2 |  | request submitted, no bidding | no | Block X
KHARKIV CHPP-5 | СHP | Unit 1,2 | Gas-insulated circuit breaker 110kV 3 phases. Type LTB145D1/B | pcs | 2 | 41700 | 240/240 MW | 1 | 2nd quarter of 2024 | 8 days from the date of delivery of the equipment |  | The need to restore equipment for switching high-voltage electrical circuits | The equipment is needed to rebuild for this winter. | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 1 | Current transformer 110kV Type IMB 123 | pcs | 3 | 15000 | 120/120 MW | 1 | 2nd quarter of 2024 | 4 days from the date of delivery of the equipment |  | The need to restore the operability of metering, protection, measurement, automation and alarm devices | The equipment is needed to rebuild for this winter. | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 1 | Transformer oil NYTRO GX11 | t | 10 | 60000 | 120/120 MW | 1 | 2nd quarter of 2024 | 5 days from the date of delivery of the equipment |  | The need to restore a power transformer | The equipment is needed to rebuild for this winter. | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 1 ,2 | Current conductor type TZMEP-10 ( 6 ) -3200 | m | 300 | 312600 | 240/240 MW | 2 | 4nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to restore equipment for the transmission and distribution of electricity |  | UESF - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Thyristor excitation system for turbine generators type SVTG-2k/300-C2T2.5-AR24-UHL4 with excitation transformer | pcs | 1 | 270900 | 120/120 MW | 1 | 4nd quarter of 2024 | 45 days from the date of delivery of the equipment |  | The need to restore power to the turbine generator field winding | It is necessary to initiate bidding for this equipment, as the turbine generator excitation system is an integral part of the generating equipment, which also includes this: A set of panels of electrical protection and automation based on PM RPA "Diamant"; Set of measuring transformers adapted to the generator current lead type IPB-AI-E-15, 75-8000-460-UHL1; Generator current lead type 10.5 kV. TEKN 20/8000 complete with measuring transformers; Generator current lead type 10.5 kV. TEKN 20/1600. | request submitted, no bidding | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Generator current lead type 10.5kV. TEKN 20/1600 | m | 90 | 135000 | 120/120 MW | 2 | 4nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to restore equipment for the transmission and distribution of electricity |  | UESF - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Generator current lead type 10.5 kV. TEKN 20/8000 complete with measuring transformers | m | 55 | 412500 | 120/120 MW | 2 | 4nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to restore equipment for the transmission and distribution of electricity |  | UESF - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Set of measuring transformers adapted to the generator current lead type IPB-AI-E-15, 75-8000-460-UHL1 | set | 1 | 400000 | 120/120 MW | 2 | 4nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to restore equipment for the transmission and distribution of electricity | The equipment is needed to rebuild for this winter. | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Voltage limiter type PEXLIM R108-YV123 | pcs | 3 | 2550 | 120/120 MW | 2 | 4nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to protect electrical equipment from high voltage pulses. | The equipment is needed to rebuild for this winter. | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 1 ,2 | Suspended, tensioned insulation and busbar of 110kV | pcs | 1 | 83350 | 240/240 MW | 2 | 4nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to restore equipment for the transmission and distribution of electricity | The equipment is needed to rebuild for this winter. | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Disconnector 110kV, Type SDF 145/1600, 3 phases, one earthing knife | pcs | 1 | 10000 | 120/120 MW | 2 | 4nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to restore equipment for switching high-voltage electrical circuits | The equipment is needed to rebuild for this winter. | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 1 ,2 | Disconnector 110kV, Type NSA 145/1600, 3 phases, two earthing knives | pcs | 2 | 24000 | 240/240 MW | 1 | 2nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to restore equipment for switching high-voltage electrical circuits | The equipment is needed to rebuild for this winter. | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 3 | Busbar ShZK-1,2-4000-81UZ RV-2 | m | 57 | 104310 | 300/300 MW | 1 | 2nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to restore equipment for the transmission and distribution of electricity | The equipment is needed to rebuild for this winter. | ESP USAID - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Electric rope hoist 3.2t/12m | pcs | 1 | 2250 | 120/120 MW | 1 | 2nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The restoration of lifting equipment is necessary to speed up and facilitate recovery, including emergency repairs. |  | request submitted, no bidding | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Materials for the restoration of the main building. | set | 1 | 120000 | 120/120 MW | 1 | 2nd quarter of 2024 | 30 days from the date of delivery of the equipment |  | The need to restore the main building | The equipment is needed to rebuild for this winter. | UESF - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Metal structures to restore the roof of the main building (3 blocks, according to the project documentation) | set | 1 | 348150 | 120/120 MW | 1 | July 15, 2024 | 30 days from the date of delivery of the equipment |  | The need to restore the building of the main building | The equipment is needed to rebuild for this winter. | UESF - in procurement | yes | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Мікропроцесорний прилад інформаційно-діагностичний комплекс "Регіна" 2ХТ | шт | 1 | 20730 | 120/120 МВт | 1 | 4 квартал 2024 року | 40 днів з дати постачання обладнання | ПРИВАТНЕ ПІДПРИЄМСТВО "АНІГЕР" | необхідність відновлення електрообладнання енергоблоку | Термін поставки підтверджуємо. | UESF - SR wasn't submitted to the Ministry. надіслано лист від 27.05.2024 № 01-11/1094 для затвердження повторного запиту, відповіді не надійшло | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Сигнальний кабель HELUKABEL TOPGEBER 511 PVC 4x2x0.34 + 4x0.5 QMM/ C E170315 c96us AWM STYLE 2448 AWM II/IA/B 60 C 30V FT1 – DESINA з роз’ємами M23, тип E, 12 контактів | м | 40 | 320 | 120/120 МВт | 1 | 4 квартал 2024 року | 41 день з дати постачання обладнання | ТОВ «Ел.Трейд». | Необхідність відновлення системи керування турбіною на енергоблоці | Термін поставки підтверджуємо | UESF - SR wasn't submitted to the Ministry. надіслано лист від 27.05.2024 № 01-11/1094 для затвердження повторного запиту, відповіді не надійшло | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Сигнальний кабель HELUKABEL TOPGEBER 511 PVC 4x2x0.34 + 4x0.5 QMM/ C E170315 c96us AWM STYLE 2448 AWM II/IA/B 60 C 30V FT1 – DESINA з роз’ємами M23, тип E, 12 контактів | м | 80 | 640 | 120/120 МВт | 1 | 4 квартал 2024 року | 42 дні з дати постачання обладнання | ТОВ «Ел.Трейд». | Необхідність відновлення системи керування турбіною на енергоблоці | Термін поставки підтверджуємо | UESF - SR wasn't submitted to the Ministry. надіслано лист від 27.05.2024 № 01-11/1094 для затвердження повторного запиту, відповіді не надійшло | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Силовий кабель HELUKABEL TOPFLEX 600-C-PVC 4G1.5 QMM / 22960 0.6/1kV з роз'ємами M23, тип P, 6-контактний | м | 40 | 200 | 120/120 МВт | 1 | 4 квартал 2024 року | 43 дні з дати постачання обладнання | ТОВ «Ел.Трейд». | Необхідність відновлення системи керування турбіною на енергоблоці | Термін поставки підтверджуємо | UESF - SR wasn't submitted to the Ministry. надіслано лист від 27.05.2024 № 01-11/1094 для затвердження повторного запиту, відповіді не надійшло | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Силовий кабель HELUKABEL TOPFLEX 600-C-PVC 4G1.5 QMM / 22960 0.6/1kV з роз'ємами M23, тип P, 6-контактний | м | 80 | 400 | 120/120 МВт | 1 | 4 квартал 2024 року | 44 дні з дати постачання обладнання | ТОВ «Ел.Трейд». | Необхідність відновлення системи керування турбіною на енергоблоці | Термін поставки підтверджуємо | UESF - SR wasn't submitted to the Ministry. надіслано лист від 27.05.2024 № 01-11/1094 для затвердження повторного запиту, відповіді не надійшло | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Датчик положення серводвигуна LVTD SL300-G-SR-11111 від eddylab GmbH | шт | 3 | 45840 | 120/120 МВт | 1 | 4 квартал 2024 року | 45 днів з дати постачання обладнання | ТОВ "ТЕХНОСЕРВІС ПРОМГРУПП". | Необхідність відновлення системи керування турбіною на енергоблоці | Термін поставки підтверджуємо | UESF - SR wasn't submitted to the Ministry. надіслано лист від 27.05.2024 № 01-11/1094 для затвердження повторного запиту, відповіді не надійшло | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Силові кабелі та муфти | встановити | 1 | 108420 | 120/120 МВ | 1 | 4 квартал 2024 року | 46 днів з дати постачання обладнання |  | необхідність відновлення пошкоджених силових кабелів | Обладнання необхідно на 4 квартал 2024 року. | UESF - SR wasn't submitted to the Ministry. Запит буде поданий до Міненерго | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Комплект перетворювачів тиску, перепаду тиску та витрати для відновлення енергоблоку № 2: - перетворювач розрідження з діапазоном вимірювання від -1 до 0 кгс/см2 у кількості 6 шт.; - перетворювач надлишкового тиску з діапазоном вимірювання від 0 до 25 кгс/м2 у кількості 6 шт.; - перетворювач надлишкового тиску з діапазоном вимірювання від 0 до 100 кгс/м2 у кількості 5 шт.; - перетворювач надлишкового тиску з діапазоном вимірювання від 0 до 250 кгс/м2 у кількості 5 шт.; - перетворювач надлишкового тиску з діапазоном вимірювання від 0 до 400 кгс/м2 у кількості 3 шт. - перетворювач надлишкового тиску з діапазоном вимірювання від 0 до 630 кгс/м2 у кількості 6 шт.; - перетворювач надлишкового тиску з діапазоном вимірювання від 0 до 600 кгс/см2 у кількості 22 шт.; - комунікатори з HART протоколом та програмним забезпеченням, сумісним з типом перетворювачів - 1 шт. | комплект | 1 | 54100 | 120/120 МВ | 1 | 4 квартал 2024 року | 46 днів з дати постачання обладнання | Honeywell | Відновлення працездатності енергоблоку | Термін поставки підтверджуємо | UESF - SR wasn't submitted to the Ministry. Запит буде поданий до Міненерго | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Комплект для вимірювання вібрації турбіни Т-110/120-130-4: - контактний однокомпонентний вихорострумовий первинний вимірювальний перетворювач ПП-ВС.01 автоматичної системи контролю вібрації та механічних величин «ПУЛЬС 1.02» у кількості 10шт.; - модуль контролю ФП-ВС цифрової обробки сигналу первинного вимірювального перетворювача автоматичної системи контролю вібрації та механічних величин «ПУЛЬС 1.02» у кількості 5шт.; - модуль дискретного вводу/вивода постійного струму TREI M954В, у кількості 4 шт. | комплект | 1 | 10000 | 120/120 МВ | 1 | 4 квартал 2024 року | 30 днів з дати постачання обладнання | ТОВ "СКБ "Вібрації та ресурсу" | Відновлення працездатності енергоблоку | Термін поставки підтверджуємо | UESF - SR wasn't submitted to the Ministry. Запит буде поданий до Міненерго | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Елегазовий вимикач типу GL-312 F1/4031 | шт | 1 | 21350 |  | 1 | 4 квартал 2024 року | 38 днів з дати постачання обладнання | ТОВ «ГЕНЕРАЛЬНА ЕНЕРГЕТИЧНА КОМПАНІЯ». | необхідність відновлення обладнання другого джерела живлення трансформатора | Обладнання необхідно на 4 квартал 2024 року. | UESF - SR wasn't submitted to the Ministry. надіслано лист від 27.05.2024 № 01-11/1094 для затвердження повторного запиту, відповіді не надійшло | no | Block X
KHARKIV CHPP-5 | СHP | Unit 2 | Трансформатор струму типу ТФЗМ -123 II-IV U1 | шт | 3 | 15330 |  | 1 | 4 квартал 2024 року | 39 днів з дати постачання обладнання | Виробнича компанія Товариство з обмеженою відповідальністю «Запорізьке трансформаторне об'єднання». | необхідність відновлення обладнання другого джерела живлення трансформатора | Обладнання необхідно на 4 квартал 2024 року. | UESF - SR wasn't submitted to the Ministry. надіслано лист від 27.05.2024 № 01-11/1094 для затвердження повторного запиту, відповіді не надійшло | no | Block X
DTEK | Generation | Burshtyn TPP | Power unit transformer 250 MVA 220 kV / 15.75 kV | pcs | 2 | 4628000 | 240 MW | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | 242 MW of generating capacity, electricity and heat supply for 193,6 thousand people |  | ESP USAID - in procurement | yes | P,K
DTEK | Generation | Burshtyn TPP | Power unit transformer 250 MVA 330 kV / 15.75 kV | pcs | 1 | 2314000 | 150 MW | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | 150 MW of generating capacity, electricity and heat supply for 120 thousand people |  | ESP USAID - in procurement | yes | N
DTEK | Transmission | Burshtyn TPP | Autotransformer 240 MVA / 330 kV / 220 kV / Yauto/d-11 | pcs | 1 | 3008000 | n/a | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | Ensuring the transmission of electricity between lines with different voltage classes and improving grid reliability |  | ESP USAID - in procurement | yes | n\a
DTEK | Transmission | Burshtyn TPP | Autotransformer 210 MVA / 400 kV / 330 kV / Yauto/d-11 | pcs | 3 | 8054000 | n/a | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | Ensuring the transmission of electricity between lines with different voltage classes and improving grid reliability |  | ESP USAID - in procurement | yes | n\a
DTEK | Transmission | Burshtyn TPP | Autotransformer 133 MVA / 400 kV / 220 kV / Yauto/d-11 | pcs | 1 | 1666000 | n/a | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | Ensuring the transmission of electricity between lines with different voltage classes and improving grid reliability |  | ESP USAID - in procurement | yes | n\a
DTEK | Transmission | Kryvoryzka TPP | Autotransformer 250 MVA / 330 kV / 150 kV | pcs | 1 | 2129000 | n/a | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | Ensuring the transmission of electricity between lines with different voltage classes and improving grid reliability |  | ESP USAID - in procurement | yes | n\a
DTEK | Generation | Kryvoryzka TPP | Power unit transformer 400 MVA /154 kV / 20 kV | pcs | 1 | 3147000 | 300 MW | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | 300 MW of generating capacity, electricity and heat supply for 232 thousand people |  | ESP USAID - in procurement | yes | F
DTEK | Generation | Ladyzhyn TPP | Power unit control system + TCS + turbine excitation system | pcs | 2 | 3888000 | 438 MW | 1 | 2024 | 60 days after supply | ABB, Siemens, Emerson, Schneider Electric | 438 MW of generating capacity, electricity and heat supply for 350 thousand people |  | ESP USAID - in procurement | yes | X,H
DTEK | Generation | Pridnyprovska TPP | Power unit transformer 250 MVA / 150 kV / 18 kV | pcs | 1 | 2684000 | 120 MW | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | 120 MW of generating capacity, electricity and heat supply for 99 thousand people |  | ESP USAID - in procurement | yes | U
DTEK | Transmission | Pridnyprovska TPP | Autotransformer 400 MVA / 330 kV / 150 kV | pcs | 2 | 6666000 | n/a | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | Ensuring the transmission of electricity between lines with different voltage classes and improving grid reliability |  | ESP USAID - in procurement | yes | n\a
DTEK | Generation | Burshtyn TPP | Auxiliary transformer 25/32 МVA | pcs | 4 | 2036000 | n/a | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | Possibility to operate the station through powering its own |  | ESP USAID - in procurement | yes | P,K,N
DTEK | Generation | Dobrotvir TPP | Power unit transformer 200 MVA / 220 kV /18 kV | pcs | 1 | 1805000 | 160 MW | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | 160 MW of generating capacity, electricity and heat supply for 128 thousand people |  | ESP USAID - in procurement | yes | W
DTEK | Generation | Kryvoryzka TPP | Excitation transformer 20 kV / 1 kV | pcs | 1 | 93000 | n/a | 1 | 2024 | 30 days after supply | ABB | Restoration of power unit operation capability |  | ESP USAID - in procurement | yes | P,K,N
DTEK | Generation | Ladyzhyn TPP | Auxiliary transformer 40 МVA | pcs | 1 | 509000 | n/a | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | Possibility to operate the station through powering its own |  | ESP USAID - in procurement | yes | P,K,N
DTEK | Generation | Burshtyn TPP | Generator 200 MW | pcs | 2 | 20800000 | 329 MW | 3 | 2025 | 90 days after supply | Ukrainian Energy Machines, GE, Siemens | 329 MW of generating capacity, electricity and heat supply for 263 thousand people | The necessity could be reconsidered after the cleaning of debris and fault detection of equipment | Not covered | no | P
DTEK | Generation | Kryvoryzka TPP | Generator 300 MW | pcs | 1 | 13500000 | 290 MW | 3 | 2025 | 90 days after supply | Ukrainian Energy Machines, GE, Siemens | 290 MW of generating capacity, electricity and heat supply for 232 thousand people | The necessity could be reconsidered after the cleaning of debris and fault detection of equipment | Not covered | no | X,H
DTEK | Generation | Kryvoryzka TPP | Turbine 300 MW | pcs | 1 | 26000000 | (#DE018) | 3 | 2025 | 330 days after supply | Ukrainian Energy Machines, GE, Siemens | (#DE018) | The necessity could be reconsidered after the cleaning of debris and fault detection of equipment | Not covered | no | V,C
DTEK | Generation | Ladyzhyn TPP | Generator 300 MW | pcs | 2 | 27000000 | 438 MW | 3 | 2025 | 90 days after supply | Ukrainian Energy Machines, GE, Siemens | 438 MW of generating capacity, electricity and heat supply for 350 thousand people | The necessity could be reconsidered after the cleaning of debris and fault detection of equipment | Not covered | no | E
DTEK | Generation | Ladyzhyn TPP | Turbine 300 MW | pcs | 1 | 26000000 | (#DE020) | 3 | 2025 | 330 days after supply | Ukrainian Energy Machines, GE, Siemens | (#DE020) | The necessity could be reconsidered after the cleaning of debris and fault detection of equipment | Not covered | no | E
DTEK | Generation | DTEK TIILIGULSKA WEP LLC | Blade BLA 79M A PA S R for 6 MW wind turbine | pcs | 1 | 800000 | 6 MW | 1 | September 2024 | 20 days after supply | Vestas | 6 MW of generating capacity | UESF - request submitted (#55/6-192/2024 dated 14.06.2024) | UESF - in procurement | yes | X,H
DTEK | Generation | DTEK TIILIGULSKA WEP LLC | Blade BLA 79M A PA S R for 6 MW wind turbine | pcs | 2 | 1500000 | 12 MW | 1 | September 2024 | 20 days after supply | Vestas | 12 MW of generating capacity | UESF - request submitted (№ 55/6-223/2024 dated 03.07.2024) | UESF - reservation of funds was requested on 02/08/2024, not confirmed by EnCS | yes | X
DTEK | Generation | DTEK POKROVSKA SOLAR FARM LLC | 150/35 kV three phase transformer 80 MVA | pcs | 1 | 900000 | 25 MW | 1 | September 2024 | 20 days after supply | ZTR (Ukraine), GE, Siemens | 25 MW | UESF - request submitted (#71/6-151/2024 dated 26.06.2024) | UESF-Approved by MoE on 12/08/2024, the reservation of funds requested (not confirmed by EnCS) | no | n\a
DTEK | Generation | DTEK POKROVSKA SOLAR FARM LLC | Power cable 35 kV, contol cable | m | 8300 | 153600 | (#DR003) | 1 | September 2024 | 20 days after supply | Large number of suppliers | (#DR003) | UESF - request submitted (#70/6-118/2024 dated 26.06.2024) | UESF - support request approved by Ministry of Energy. Awaiting for the transfer for funds reservation to Energy Community | yes | n\a
DTEK | Generation | DTEK POKROVSKA SOLAR FARM LLC | Distribution 35 kV Switchgear type KYN61-40.5 (35 kV, 2000A, 25 kA) | pcs | 2 | 1300000 | (#DR003) | 1 | September 2024 | 20 days after supply | Siemens | (#DR003) | UESF - request submitted (#70/6-118/2024 dated 26.06.2024) | UESF - support request approved by Ministry of Energy. Awaiting for the transfer for funds reservation to Energy Community | yes | n\a
DTEK | Generation | DTEK NIKOPOLSKA SOLAR FARM LLC | Solar panels Trina Solar 330 Wp and Seraphim 330 Wp | pcs | 750 | 54450 | 3 MW | 1 | September 2024 | 20 days after supply | Shanghai JA Solar Technology | 3 MW of generating capacity | UESF - request submitted (#70/6-122/2024 dated 03.07.2024) | UESF - Rejected by MoE on 02/08/2024 | no | n\a
DTEK | Generation | DTEK POKROVSKA SOLAR FARM LLC | Solar panels Risen RSM72-6-370М 370 Wp | pcs | 4860 | 395604 | 4 MW | 1 | September 2024 | 20 days after supply | Shanghai JA Solar Technology | 4 MW of generating capacity | UESF - request submitted (#71/6-157/2024 dated 03.07.2024) | UESF - Rejected by MoE ON 02/08/2024 | no | n\a
DTEK | Transmission | Kryvoryzka TPP | Autotransformer 250 MVA / 330 kV / 150 kV | pcs | 1 | 2270000 | n/a | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | Ensuring the transmission of electricity between lines with different voltage classes and improving grid reliability | Energy Community UESF - in procurement | UESF - in procurement | no | n\a
DTEK | Generation | Pridnyprovska TPP | Power unit transformer 250 MVA / 150 kV / 18 kV | pcs | 1 | 2270000 | 125 MW | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | 125 MW of generating capacity, electricity and heat supply for 100 thousand people | Energy Community UESF - in procurement | UESF - in procurement | no | n\a
DTEK | Generation | Kryvoryzka TPP | Power unit transformer 400 MVA /154 kV / 20 kV | pcs | 1 | 3100000 | 289 MW | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | 289 MW of generating capacity, electricity and heat supply for 230 thousand people | Energy Community UESF - in procurement | UESF - in procurement | no | n\a
DTEK | Generation | Dobrotvir TPP | Power unit transformer 200 MVA / 220 kV /18 kV | pcs | 1 | 2000000 | 160 MW | 1 | 2024 | 60 days after supply | ZTR (Ukraine), GE, Siemens | 160 MW of generating capacity, electricity and heat supply for 130 thousand people | UESF - request submitted (#83/611 dated 29.05.2024) | Approved by the Ministry of Energy on 07.06.2024. Funds reservation requested | no | S
DTEK | Generation | Burshtyn TPP | Power unit control system + TCS + turbine excitation system | pcs | 1 | 1900000 | 190 MW | 1 | 2024 | 60 days after supply | ABB, Siemens, Emerson, Schneider Electric | 190 MW of generating capacity, electricity and heat supply for 150 thousand people | UESF - request submitted (#83/611 dated 29.05.2024) | Approved by the Ministry of Energy on 07.06.2024. Funds reservation requested | no | P
DTEK | Generation | Burshtyn TPP | Equipment and materials for repairing damaged units (generator spare parts, pumps, pipes, transformer and turbine oil, cable) | - |  | 2916240 | n/a | 1.1 | September 2024 | 60 days after supply | Different manufacturers | Contributes to the restoration of 300 MW of power capacity | UESF - request submitted (#83/611 dated 29.05.2024) | Approved by the Ministry of Energy on 07.06.2024. Funds reservation requested, not confirmed by EnCS | no | I
DTEK | Generation | Ladyzhyn TPP | Equipment and materials for repairing damaged units (pipes, pumps, transformer oil, cable) | - |  | 4069390 | n/a | 1.1 | September 2024 | 60 days after supply | Different manufacturers | Contributes to the restoration of 438 MW of power capacity | UESF - request submitted (#83/611 dated 29.05.2024) | Approved by the Ministry of Energy on 07.06.2024. Funds reservation requested, not confirmed by EnCS | no | V
DTEK | Generation | Dobrotvir TPP | Equipment and materials for repairing damaged units (pipes, transformer oil, cable, shielded conductors) | - |  | 1724370 | n/a | 1.1 | September 2024 | 60 days after supply | Different manufacturers | Contributes to the restoration of 320 MW of power capacity | UESF - request submitted (#83/611 dated 29.05.2024) | Approved by the Ministry of Energy on 07.06.2024. Funds reservation requested, not confirmed by EnCS | no | F,V,N
DTEK | Generation | Burshtyn TPP | Specialized construction equipment (truck cranes, excavator, backhoe loader, tipper truck, truck with a manipulator, articulated boom lift, flatbed truck, forklift truck, tractor unit, semi-trailer) | pcs | 11 | 2444100 | n/a | 1.1 | September 2024 | n/a | Different manufacturers | Acceleration of recovery operations of damaged power units | UESF - request submitted (#83/714 dated 25.06.2024) | Awaiting for the Ministry's of Energy consideration under the established procedure | no | X,H
DTEK | Generation | Dobrotvir TPP | Specialized construction equipment (truck crane, hydraulic car lift, excavator,articulated boom lift,truck with a manipulator) | pcs | 6 | 762000 | n/a | 1.1 | September 2024 | n/a | Different manufacturers | Acceleration of recovery operations of damaged power units | UESF - request submitted (#83/714 dated 25.06.2024) | Awaiting for the Ministry's of Energy consideration under the established procedure | no | I,W
DTEK | Generation | Ladyzhyn TPP | Specialized construction equipment (truck with a manipulator, excavator, backhoe loader, truck cranes, tipper truck, tractor unit, semi-trailer for a truck tractor, articulated boom lifts) | pcs | 10 | 2309100 | n/a | 1.1 | September 2024 | n/a | Different manufacturers | Acceleration of recovery operations of damaged power units | UESF - request submitted (#83/714 dated 25.06.2024) | Awaiting for the Ministry's of Energy consideration under the established procedure | no | F,V,N
DTEK | Generation | WE maintenance | Specialized construction equipment (truck with a manipulator, trailer, truck crane, tractor unit, semi-trailer, telescopic loader, hydraulic system for moving heavy loads with rails) | pcs | 14 | 2314350 | n/a | 1.1 | September 2024 | n/a | Different manufacturers | Acceleration of recovery operations of damaged power units | UESF - request submitted (#83/714 dated 25.06.2024) | Awaiting for the Ministry's of Energy consideration under the established procedure | no | I,W
DTEK | Generation | Pridnyprovska TPP | Specialized equipment for debris removal and remediation (truck with a manipulator, hydraulic car lift, excavator, articulated boom lifts) | pcs | 5 | 502000 | n/a | 1.1 | September 2024 | n/a | Different manufacturers | Acceleration of recovery operations | UESF - request submitted (#01/433 dated 12.06.2024) | UESF - Approved by the Ministry of Energy on 01.07.2024. Funds reservation requested, not confirmed by EnCS | no | X,H
DTEK | Generation | Kryvoryzka TPP | Specialized equipment for debris removal and remediation (truck with a manipulator, hydraulic car lift, excavator, truck crane, tractor unit, semi trailer, articulated boom lifts) | pcs | 8 | 2139100 | n/a | 1.1 | September 2024 | n/a | Different manufacturers | Acceleration of recovery operations | UESF - request submitted (#01/433 dated 12.06.2024) | UESF - Approved by the Ministry of Energy on 01.07.2024. Funds reservation requested, not confirmed by EnCS | no | n/a
DTEK | Generation | Burshtyn TPP | Recovery and replacement of the damaged turbine and boiler departments’ equipment. Recovery of the main and supporting building structures: roofs, walls, columns, window openings, control room premises, switchgear room, workshops, supporting structures of the current lines, etc. | set | 1 | 37800000 | n/a | 1 | 2024 | 60-90 days after supply | Wide range of products, large number of suppliers | Equipment, materials for repairing damaged units and infrastructure. Contribute to the overall restoration to ensure 438 MW of power capacity | UESF - requests submitted (#83/816 dated 30.07.2024, #83/828 dated 01.08.2024) | Two requests were submitted for the amount of EUR 37,8 mln (materials and equipment). Awaiting the Ministry of Energy approval and transfer for funds reservation to Energy Community | yes | U,O,S
DTEK | Generation | Burshtyn TPP | Recovery and replacement of the damaged turbine and boiler departments’ equipment. Recovery of the main and supporting building structures: roofs, walls, columns, window openings, control room premises, switchgear room, workshops, supporting structures of the current lines, etc. | set | 1 | 9400000 | n/a | 1.1 | 2024 | 60-90 days after supply | Wide range of products, large number of suppliers | Services for repairing damaged units and infrastructure. Contribute to the overall restoration to ensure 438 MW of power capacity |  | Not covered | no | P,K
DTEK | Generation | Dobrotvir TPP | Recovery and replacement of the damaged turbine and boiler departments’ equipment. Recovery of the main and supporting building structures: roofs, walls, columns, window openings, control room premises, switchgear room, workshops, supporting structures of the current lines, etc. | set | 1 | 11200000 | n/a | 1 | 2024 | 60-90 days after supply | Wide range of products, large number of suppliers | Equipment, materials for repairing damaged units and infrastructure. Contribute to the overall restoration to ensure 438 MW of power capacity | UESF - requests submitted (#83/816 dated 30.07.2024, #83/828 dated 01.08.2024) | Two requests were submitted for the amount of EUR 11,2 mln (materials and equipment). Awaiting for the Ministry of Energy approval and transfer for funds reservation to Energy Community | yes | F,E,V,N,C
DTEK | Generation | Dobrotvir TPP | Recovery and replacement of the damaged turbine and boiler departments’ equipment. Recovery of the main and supporting building structures: roofs, walls, columns, window openings, control room premises, switchgear room, workshops, supporting structures of the current lines, etc. | set | 1 | 4400000 | n/a | 1.1 | 2024 | 60-90 days after supply | Wide range of products, large number of suppliers | Services for repairing damaged units and infrastructure. Contribute to the overall restoration to ensure 438 MW of power capacity |  | Not covered | no | I,W
DTEK | Generation | Ladyzhyn TPP | Recovery and replacement of the damaged turbine and boiler departments’ equipment. Recovery of the main and supporting building structures: roofs, walls, columns, window openings, control room premises, switchgear room, workshops, supporting structures of the current lines, etc. | set | 1 | 8800000 | n/a | 1 | 2024 | 60-90 days after supply | Wide range of products, large number of suppliers | Equipment, materials for repairing damaged units and infrastructure. Contribute to the overall restoration to ensure 438 MW of power capacity | UESF - request submitted (#83/828 dated 01.08.2024) | UESF - support request was approved by MoE ON 02/08/2024, the funds were pre-reserved (reservation ahead) Awaiting for the Ministry of Energy approval and transfer for funds reservation to Energy Community | yes | X,H
DTEK | Generation | Ladyzhyn TPP | Recovery and replacement of the damaged turbine and boiler departments’ equipment. Recovery of the main and supporting building structures: roofs, walls, columns, window openings, control room premises, switchgear room, workshops, supporting structures of the current lines, etc. | set | 1 | 42500000 | n/a | 1.1 | 2024 | 60-90 days after supply | Wide range of products, large number of suppliers | Services for repairing damaged units and infrastructure. Contribute to the overall restoration to ensure 438 MW of power capacity |  | Not covered | no | P,K
DTEK | Generation | Kryvoryzka TPP | Recovery and replacement of the damaged turbine and boiler departments’ equipment. Recovery of the main and supporting building structures: roofs, walls, columns, window openings, control room premises, switchgear room, workshops, supporting structures of the current lines, etc. | set | 1 | 8100000 | n/a | 1.1 | 2024 | 60-90 days after supply | Wide range of products, large number of suppliers | Equipment, materials, and services for repairing damaged units and infrastructure. Contribute to the overall restoration to ensure 729 MW of power capacity | Loans or grant financing is required | Not covered | no | U,O,S
DTEK | Generation | Pridnyprovska TPP | Recovery and replacement of the damaged turbine and boiler departments’ equipment. Recovery of the main and supporting building structures: roofs, walls, columns, window openings, control room premises, switchgear room, workshops, supporting structures of the current lines, etc. | set | 1 | 8800000 | n/a | 1.1 | 2024 | 60-90 days after supply | Wide range of products, large number of suppliers | Equipment, materials, and services for repairing damaged units and infrastructure. Contribute to the overall restoration to ensure 215 MW of power capacity | Loans or grant financing is required | Not covered | no | n\a
DTEK | Generation | DTEK Westenergy | Open cycle gas turbine (OCGT) General Electric LM6000 PG 56 MW | pcs | 2 | 60000000 | 112 MW | 1 | 2024 | 2025 | GE VERNOVA | New construction 112 MW |  | Not covered | no | n\a
DTEK | Generation | DTEK Westenergy | Gas booster compressors | pcs | 2 | 10200000 | (#DE041) | 1 | 2024 | 2025 | Ariel Corp | (#DE041) |  | Not covered | no | n\a
DTEK | Generation | DTEK Westenergy | Ggrid connection equipment-step-up power transformer 80 MVA, other HV equipment | set | 2 | 6400000 | (#DE041) | 1 | 2024 | 2025 | GE VERNOVA | (#DE041) |  | Not covered | no | n\a
DTEK | Generation | DTEK Westenergy | Civil, Instalation and commissioning works | set | 2 | 26500000 | (#DE041) | 1 | 2024 | 2025 | Large number of suppliers | (#DE041) |  | Not covered | no | n\a
DTEK | Generation | DTEK Westenergy | Protective shelter | pcs | 2 | 11000000 | (#DE041) | 1 | 2024 | 2025 | Large number of suppliers | (#DE041) |  | Not covered | no | F,E,V,N,C
DTEK | Generation | Burshtyn TPP | Hot-dip galvanised steel trusses with tarpaulin roof 870m2 х 2,5m(h) | pcs | 1 | 182000 | n/a | 1 | ASAP | Sep 2024 | Layher, AT-PAC, Bil-Jax | The provision of temporary protective structures will provide an opportunity to protect electric equipment from weather conditions and mitigate possible short circuits and equipment failure, providing an opportunity to operate with equipment during the absence of roofs. It will ensure the possibility of operating a power unit with 180 MW capacity, which will provide electricity to approximately 140 thousand people. Installation works will be carried out independently. |  | Not covered | no | F,E,V,N,C
DTEK | Generation | Burshtyn TPP | Hot-dip galvanised steel trusses with tarpaulin roof 90m2 х 4,0m(h) | pcs | 1 | 28000 | n/a | 1 | ASAP | Oct 2024 | Layher, AT-PAC, Bil-Jax | The provision of temporary protective structures will provide an opportunity to protect electric equipment from weather conditions and mitigate possible short circuits and equipment failure, providing an opportunity to operate with equipment during the absence of roofs. It will ensure the possibility of operating a power unit with 150 MW capacity, which will provide electricity to approximately 120 thousand people. Installation works will be carried out independently. |  | Not covered | no | I,W
DTEK | Generation | Dobrotvir TPP | Hot-dip galvanised steel trusses with tarpaulin roof 90m2 х 2,5m(h) | pcs | 1 | 26000 | n/a | 1 | ASAP | Oct 2024 | Layher, AT-PAC, Bil-Jax | The provision of temporary protective structures will provide an opportunity to protect electric equipment from weather conditions and mitigate possible short circuits and equipment failure, providing an opportunity to operate with equipment during the absence of roofs. It will ensure the possibility of operating a power unit with 150 MW capacity, which will provide electricity to approximately 120 thousand people. Installation works will be carried out independently. |  | Not covered | no | I,W
DTEK | Generation | Dobrotvir TPP | Hot-dip galvanised steel trusses with tarpaulin roof 240 m2 х 4,0 m(h) | pcs | 1 | 54000 | n/a | 1 | ASAP | Nov 2024 | Layher, AT-PAC, Bil-Jax | The provision of temporary protective structures will provide an opportunity to protect electric equipment from weather conditions and mitigate possible short circuits and equipment failure, providing an opportunity to operate with equipment during the absence of roofs. It will ensure the possibility of operating a power unit with 160 MW capacity, which will provide electricity to approximately 130 thousand people. Installation works will be carried out independently. |  | Not covered | no | X,H
DTEK | Generation | Ladyzhyn TPP | Hot-dip galvanised steel trusses with tarpaulin roof 1200 m2 х 4,0 m(h) | pcs | 1 | 262000 | n/a | 1 | ASAP | Dec 2024 | Layher, AT-PAC, Bil-Jax | The provision of temporary protective structures will provide an opportunity to protect electric equipment from weather conditions and mitigate possible short circuits and equipment failure, providing an opportunity to operate with equipment during the absence of roofs. It will ensure the possibility of operating a power unit with 240 MW capacity, which will provide electricity to approximately 190 thousand people. Installation works will be carried out independently. |  | Not covered | no | P,K
DTEK | Generation | Kryvoryzka TPP | Hot-dip galvanised steel trusses with tarpaulin roof 720m2 х 4,0 m(h) | pcs | 1 | 159000 | n/a | 1 | ASAP | Sep 2024 | Layher, AT-PAC, Bil-Jax | The provision of temporary protective structures will provide an opportunity to protect electric equipment from weather conditions and mitigate possible short circuits and equipment failure, providing an opportunity to operate with equipment during the absence of roofs. It will ensure the possibility of operating a power unit with 289 MW capacity, which will provide electricity to approximately 230 thousand people. Installation works will be carried out independently. |  | Not covered | no | P,K
DTEK | Generation | Kryvoryzka TPP | Hot-dip galvanised steel trusses with tarpaulin roof 390m2 х 8,0 m(h) | pcs | 1 | 100000 | n/a | 1 | ASAP | Sep 2024 | Layher, AT-PAC, Bil-Jax | The provision of temporary protective structures will provide an opportunity to protect electric equipment from weather conditions and mitigate possible short circuits and equipment failure, providing an opportunity to operate with equipment during the absence of roofs. It will ensure the possibility of operating a power unit with 289 MW capacity, which will provide electricity to approximately 230 thousand people. Installation works will be carried out independently. |  | Not covered | no | U,O,S
DTEK | Generation | Pridnyprovska TPP | Hot-dip galvanised steel trusses with tarpaulin roof 1140m2 х 4,0 m(h) | pcs | 1 | 247000 | n/a | 1 | ASAP | Nov 2024 | Layher, AT-PAC, Bil-Jax | The provision of temporary protective structures will provide an opportunity to protect electric equipment from weather conditions and mitigate possible short circuits and equipment failure, providing an opportunity to operate with equipment during the absence of roofs. It will ensure the possibility of operating a power unit with 90 MW capacity, which will provide electricity to approximately 70 thousand people. Installation works will be carried out independently. |  | Not covered | no | U,O,S
DTEK | Generation | Pridnyprovska TPP | Hot-dip galvanised steel trusses with tarpaulin roof 240m2 х 2,5 m(h) | pcs | 1 | 52000 | n/a | 1 | ASAP | Nov 2024 | Layher, AT-PAC, Bil-Jax | The provision of temporary protective structures will provide an opportunity to protect electric equipment from weather conditions and mitigate possible short circuits and equipment failure, providing an opportunity to operate with equipment during the absence of roofs. It will ensure the possibility of operating a power unit with 90 MW capacity, which will provide electricity to approximately 70 thousand people. Installation works will be carried out independently. |  | Not covered | no | U,O,S
DTEK | Generation | Pridnyprovska TPP | Compressor units for the power plant compressor station | pcs | 2 | 139000 | n/a | 2 | 2025 | 60-90 days after supply | BTS Group Kyiv | To supply compressed air for repairs |  | Not covered | no | P,K
DTEK | Generation | Kryvoryzka TPP | Compressor units for the power plant compressor station | pcs | 2 | 139000 | n/a | 2 | 2025 | 60-90 days after supply | BTS Group Kyiv | To supply compressed air for repairs |  | Not covered | no | F,E,V,N,C
DTEK | Generation | Burshtyn TPP | Compressor units for the power plant compressor station | pcs | 2 | 139000 | n/a | 2 | 2025 | 60-90 days after supply | BTS Group Kyiv | To supply compressed air for repairs |  | Not covered | no | I,W
DTEK | Generation | Dobrotvir TPP | Compressor units for the power plant compressor station | pcs | 2 | 139000 | n/a | 2 | 2025 | 60-90 days after supply | BTS Group Kyiv | To supply compressed air for repairs |  | Not covered | no | U,O,S
DTEK | Generation | Pridnyprovska TPP | Boiler and turbine room cranes | pcs | 4 | 3515000 | n/a | 2 | 2025 | 60-90 days after supply | Kyiv Crane Machinery Plant LLC | Restore damaged equipment and thus ensure repair of the main production equipment (boiler, turbine, generator) |  | Not covered | no | P,K
DTEK | Generation | Kryvoryzka TPP | Boiler and turbine room cranes | pcs | 4 | 3515000 | n/a | 2 | 2025 | 60-90 days after supply | Kyiv Crane Machinery Plant LLC | Restore damaged equipment and thus ensure repair of the main production equipment (boiler, turbine, generator) |  | Not covered | no | X,H
DTEK | Generation | Ladyzhyn TPP | Boiler and turbine room cranes | pcs | 4 | 3515000 | n/a | 2 | 2025 | 60-90 days after supply | Kyiv Crane Machinery Plant LLC | Restore damaged equipment and thus ensure repair of the main production equipment (boiler, turbine, generator) |  | Not covered | no | F,V
DTEK | Generation | Burshtyn TPP | Boiler and turbine room cranes | pcs | 4 | 3515000 | n/a | 2 | 2025 | 60-90 days after supply | Kyiv Crane Machinery Plant LLC | Restore damaged equipment and thus ensure repair of the main production equipment (boiler, turbine, generator) |  | Not covered | no | I,W
DTEK | Generation | Dobrotvir TPP | Boiler and turbine room cranes | pcs | 4 | 3515000 | n/a | 2 | 2025 | 60-90 days after supply | Kyiv Crane Machinery Plant LLC | Restore damaged equipment and thus ensure repair of the main production equipment (boiler, turbine, generator) |  | Not covered | no | U,O,S
DTEK | Generation | Pridnyprovska TPP | Electrolysis units | pcs | 2 | 510000 | n/a | 2 | 2025 | 60-90 days after supply | CRYO Inter TradingKyiv | To ensure the production of hydrogen and thus the operation of the TPP |  | Not covered | no | P,K
DTEK | Generation | Kryvoryzka TPP | Electrolysis units | pcs | 2 | 510000 | n/a | 2 | 2025 | 60-90 days after supply | CRYO Inter TradingKyiv | To ensure the production of hydrogen and thus the operation of the TPP |  | Not covered | no | X,H
DTEK | Generation | Ladyzhyn TPP | Electrolysis units | pcs | 2 | 510000 | n/a | 2 | 2025 | 60-90 days after supply | CRYO Inter TradingKyiv | To ensure the production of hydrogen and thus the operation of the TPP |  | Not covered | no | F,E,V,N,C
DTEK | Generation | Burshtyn TPP | Electrolysis units | pcs | 2 | 510000 | n/a | 2 | 2025 | 60-90 days after supply | CRYO Inter TradingKyiv | To ensure the production of hydrogen and thus the operation of the TPP |  | Not covered | no | I,W
DTEK | Generation | Dobrotvir TPP | Electrolysis units | pcs | 2 | 510000 | n/a | 2 | 2025 | 60-90 days after supply | CRYO Inter TradingKyiv | To ensure the production of hydrogen and thus the operation of the TPP |  | Not covered | no | U,O,S
DTEK | Generation | Pridnyprovska TPP | Vehicle-based high-voltage laboratories | pcs | 1 | 269000 | n/a | 2 | September 2024 | n/a | PRILAT LLC, Kharkiv | To ensure a rapid recovery from shelling |  | Not covered | no | P,K
DTEK | Generation | Kryvoryzka TPP | Vehicle-based high-voltage laboratories | pcs | 1 | 269000 | n/a | 2 | September 2024 | n/a | PRILAT LLC, Kharkiv | To ensure a rapid recovery from shelling |  | Not covered | no | X,H
DTEK | Generation | Ladyzhyn TPP | Vehicle-based high-voltage laboratories | pcs | 1 | 269000 | n/a | 2 | September 2024 | n/a | PRILAT LLC, Kharkiv | To ensure a rapid recovery from shelling |  | Not covered | no | F,E,V,N,C
DTEK | Generation | Burshtyn TPP | Vehicle-based high-voltage laboratories | pcs | 1 | 269000 | n/a | 2 | September 2024 | n/a | PRILAT LLC, Kharkiv | To ensure a rapid recovery from shelling |  | Not covered | no | I,W
DTEK | Generation | Dobrotvir TPP | Vehicle-based high-voltage laboratories | pcs | 1 | 269000 | n/a | 2 | September 2024 | n/a | PRILAT LLC, Kharkiv | To ensure a rapid recovery from shelling |  | Not covered | no | P,K
DTEK | Generation | Kryvoryzka TPP | Crawler bulldozer (CAT D6GC or analogue) | pcs | 1 | 550000 | n/a | 1 | Decemeber 2024 | n/a | Caterpillar, Komatsu, Hyundai | Acceleration of recovery operations |  | Not covered | no
Naftogaz | Gas Distribution | LLC "Gas Distribution Networks of Ukraine" | ERW steel ріре (DN250-1 ООО) | m | 750 | [5 empty] | AB Metal Group | Provision of natural gas to households |  |  | no
Naftogaz | Gas Distribution | LLC "Gas Distribution Networks of Ukraine" | Polyethylene pipes for combustible gas distribution РЕ 100 SDR-17.6 | m | 520 | [5 empty] | AB Metal Group | Provision of natural gas to households |  |  | no
Naftogaz | Gas Distribution | LLC "Gas Distribution Networks of Ukraine" | Flanged ЬаІІ valve, full Ьоге 11с336п PN16 with reducer | pcs. | 24 | [5 empty] | AB Metal Group | Provision of natural gas to households |  |  | no
Naftogaz | Gas Distribution | LLC "Gas Distribution Networks of Ukraine" | ВаІІ valve DN 350-1000 PN 25 (flanged) | pcs. | 48 | [5 empty] | AB Metal Group | Provision of natural gas to households |  |  | no
Naftogaz | Gas Distribution | LLC "Gas Distribution Networks of Ukraine" | Flanged welded ЬаІІ valve, full Ьоге 11с337п DN250-300 PN25 with reducer | pcs. | 24 | [5 empty] | AB Metal Group | Provision of natural gas to households |  |  | no
Naftogaz | Gas Distribution | LLC "Gas Distribution Networks of Ukraine" | ВаІІ valve DN 400-600 PN 25 | pcs. | 28 | [5 empty] | AB Metal Group | Provision of natural gas to households |  |  | no
Naftogaz | Gas Distribution | LLC "Gas Distribution Networks of Ukraine" | Welded ЬаІІ valve with installation above ground level DN 70 0 | pcs. | 6 | [5 empty] | AB Metal Group | Provision of natural gas to households |  |  | no
Naftogaz | Gas production | JSC Ukrgasvydobuvannya (UGV) | Propane freeze-out unit 0=100-6000 tcm/day | pcs. | 8 | [5 empty] | Eneflex/ QB Jomsom/Propak Systems | Commodity gas quality assurance and improved gas condensate & LPG extraction |  |  | no
Naftogaz | Gas production | JSC Ukrgasvydobuvannya (UGV) | Gas piston compressor with gas piston drive, Qg = 58-540 tcm/day | pcs. | 10 | [5 empty] | EGS, Eneflex | Maintaining and ramping-up gas production |  |  | no
Naftogaz | Gas production | JSC Ukrgasvydobuvannya (UGV) | Gas piston compressorwith gas piston engine drive | pcs. | 5 | [5 empty] | EGS, Eneflex | Maintaining and ramping-up gas production |  |  | no
Naftogaz | Gas production | JSC Ukrgasvydobuvannya (UGV) | Gas turbine drive with centrifugal compressor | pcs. | 6 | [5 empty] | SolarTurbimes | Maintaining and ramping-up gas production |  |  | no
Naftogaz | Heating | JSC "Odessa CHP" | Disconnector 110kW Disconnector 110 kW РДЗ-1-110/1000 | pcs. | 7 | 16288 | 20/68 MW | 1 | 15.09.2024 | 15.11.2024 | ABB | Ensuring reliable heat supply and power generation | 560 566, 00 Euros, excl. VAT (68 МВт/ 779 Gcal ) |  | no
Naftogaz | Heating | JSC "Odessa CHP" | Disconnector 110 kW Disconnector 110 kW РДЗ-2-110/1 ООО | pcs. | 9 | 20942 | 28/68 MW | 1 | 15.09.2024 | 15.11.2024 | ABB | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | JSC "Odessa CHP" | Vacuum circuit breaker ВРЗ5НС outdoor installation, electromagnetically operated, with locking in the working position. Remote control. | pcs. | 11 | 89587 | 20/68 MW | 1 | 10.09.2024 | 15.11.2024 | ABB, schneider electric | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | JSC "Odessa CHP" | Vacuum circuit breaker 6-10 kW ВР1 | pcs. | 50 | 121000 | 38/68 MW | 1 | 15.09.2024 | 15.11.2024 | ABB, schneider electric | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | JSC "Odessa CHP" | Соге switch ВРС-11 О | pcs. | 7 | 182431 | 10/68 MW | 1 | 15.09.2024 | 15.11.2024 | ABB, schneider electric | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | JSC "Odessa CHP" | Pump type СЕ 1250-140-11 with electric motor, skid-mounted | pcs. | 7 | 130308 | 779/779 Gсal | 1 | 01.09.2024 | 1.11.2024 | Wilo | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | JSC "KRYVORIZKA TEPLOSENTRAL" | Network pump СЕ 800/100 | set | 1 | 98662 | 20/1406 Gcal | 1 | 01.09.2024 | 1.11.2024 | WILO SE, Grundfos | Ensuring reliable heat supply | 2 024 430,00 Euros, excl. VAT (4х1406 Gcal ) |  | no
Naftogaz | Heating | JSC "KRYVORIZKA TEPLOSENTRAL" | Network pump СЕ 1250/140 | set | 3 | 455148 | 90/1406 Gcal | 1 | 01.09.2024 | 1.11.2024 | WILO SE, Grundfos | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | JSC "KRYVORIZKA TEPLOSENTRAL" | Water treatment system for heat supply system іп modular design, system capacity: 100 cubic metres/hour | system | 1 | 1470620 | 200/1406 Gcal | 1 | 01.09.2024 | 15.10.2024 | ТОВ «НВО «ЕКОСОФТ» | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | JSC “Kherson CHP” | АВВ Gas circuit breaker type LTB 170 D1/B ог GENERA L ENERGY GL313 F1/4031P | set | 6 | 489382 | 40/80 MW | 1 | 01.09.2024 | 1.11.2024 | GENERAL ENERGY | Ensuring reliable heat supply and power generation | 799 246,00 Euros, excl. VAT (80 МВт ) |  | no
Naftogaz | Heating | JSC “Kherson CHP” | 154 kV disconnector type РДЗ-2-150/1000 У1, with drive | set | 14 | 240940 | 40/80 MW | 1 | 01.09.2024 | 1.11.2024 | GENERAL ENERGY, ABB | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | JSC “Kherson CHP” | Current transformer ІВМ (170 kV) ог series ТФЗМ-170-I У1, 600/5 | set | 6 | 10120 | 10/80 MW | 1 | 01.09.2024 | 15.10.2024 | GENERAL ENERGY, ABB | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | JSC “Kherson CHP” | Voltage transformer EMF (154 kV) | set | 2 | 31646 | 10/80 MW | 1 | 01.09.2024 | 15.10.2024 | ABB | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | JSC “Kherson CHP” | Surge arrester PEXLIM Q144-XH170 | set | 3 | 27158 | 10/80 MW | 1 | 01.09.2024 | 15.10.2024 | Hitachi Energy | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | JSC“Dniprovs'ka“ CHP | Power transformer 500 kVa, 6300/23V, Connection scheme wye-wye-5 and Wye-delta-100 | Unit | 1 | 6981 | 5/61,6 MW | 1 | 01.09.2024 | 15.10.2024 | ТОВ«ЛТЕХКОМ» | Ensuring reliable heat supply and power generation | 90 288,00 Euros, excl. VAT (80 МВт ) |  | no
Naftogaz | Heating | JSC“Dniprovs'ka“ CHP | Network pump Д-1250-125 1250tph, Head 125m 1480R/min, 630kW Voltage 6000V | Unit | 1 | 68877 | 150/313 Gcal | 1 | 01.09.2024 | 15.10.2024 | УКРНАСОСПРОМ | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | JSC“Dniprovs'ka“ CHP | Pressure regulator ITRON 3000 mЗ/h, lnlet pressure 0.6 bar, Outlet pressure 0.25 Ьаг, Number of reduction lines-2 | Unit | 1 | 14430 | 100/313 Gcal | 1 | 01.09.2024 | 15.10.2024 | ТОВ «ІВЦ «Європрилад» Україна | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Power transformer ТРДНС-32000/35-У1 | pcs. | 1 | 740257 | 20/40 MW | 1 | 01.09.2024 | 15.10.2024 | PJSC"Zaporozhtransformator" | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Lube оіІ сооІег МП-21 | pcs. | 4 | 372309 | 18/40 MW | 1 | 01.09.2024 | 15.10.2024 | Spetzpromarmatura | Ensuring reliable heat supply and power generation |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Wilo Atmos GIGA-N 40/160-4/2 pump set | pcs. | 1 | 4430 | 20/410 Gcal | 1 | 01.09.2024 | 15.10.2024 | Spetzpromarmatura | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Wilo Atmos GIGA-N 50/200-11/2 pump set | pcs. | 2 | 11944 | 20/410 Gcal | 1 |  | September 2023 | Spetzpromarmatura | Ensuring reliable heat supply |  | received. installed: Pumping group 40-200-7,5 2 pcs with control device | yes
Naftogaz | Heating | Mykolaiv CHP | Wilo SCP-200-360-HB stainless pump set | pcs. | 1 | 58064 | 50/410 Gcal | 1 | 15.09.2024 | 15.11.2024 | Spetzpromarmatura | Ensuring reliable heat supply | 2 207 338,00 Euros, excl. VAT (40 МВт/410 Gcal ) |  | no
Naftogaz | Heating | Mykolaiv CHP | Wilo Atmos GIGA-8 125/305-37/4-Р6 pump set | pcs. | 2 | 17059 | 40/410 Gcal | 1 | 15.09.2024 | 15.11.2024 | Spetzpromarmatura | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Wilo Atmos GIGA-B 80/170-30/2 pump set | pcs. | 1 | 10471 | 35/410 Gcal | 1 | 15.09.2024 | 15.11.2024 | Spetzpromarmatura | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Wilo Atmos GIGA-B 65/215-22/2 pump set | pcs. | 2 | 16421 | 25/410 Gcal | 1 | 15.09.2024 | 15.11.2024 | Spetzpromarmatura | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Pumping group: Wilo Yonos GIGA-N 50/200-18,5/2-R1 pump - 3 pcs with control device | pcs. | 1 | 50113 | 20/410 Gcal | 1 |  | August 2023 | Spetzpromarmatura | Ensuring reliable heat supply |  | received. installed: Pumping group 50-200-18,5 3 pcs with control device | yes
Naftogaz | Heating | Mykolaiv CHP | Wilo SCP 200/460HA-160/4-FC pump set | pcs. | 1 | 58892 | 50/410 Gcal | 1 | 15.09.2024 | 15.11.2024 | Spetzpromarmatura | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Wilo FA10.65E pump (with FK202H-4/22 drive, EMU pump, horizontal installation) | pcs. | 4 | 85440 | 25/410 Gcal | 1 | 15.09.2024 | 15.11.2024 | Spetzpromarmatura | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Wilo Atmos GIGA-N 80/200-30/2 pump set | pcs. | 3 | 31095 | 30/410 Gcal | 1 | 15.09.2024 | 15.11.2024 | Spetzpromarmatura | Ensuring reliable heat supply |  |  | no
Naftogaz | Heating | Mykolaiv CHP | Wilo SCP 250/700DV-630/4/6kV-R1/E1-FC pump set with 6000 V frequency converter | pcs. | 2 | 812900 | 60/410 Gcal | 1 | 15.09.2024 | 15.11.2024 | Spetzpromarmatura | Ensuring reliable heat supply |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Above-ground ЬаІІ valve ON 1 ОО PN150 (ANSI 900) with pneumatic actuator | pcs. | 58 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Fountain-type fitting | pcs. | 6 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Casing Head Assembly | pcs. | 6 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Gate valve 2 9/16" (65 mm) 3000 psi (2 1 Мра) | pcs. | 50 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Gate valve 4 1/16" (100 mm) 3000 psi (21 Мра) | pcs. | 50 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Manual ram blow-out preventer 7 1/16" х 3000 PSI | pcs. | 3 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | High performance motor pump (60 I/s) with discharge hose L=300m. | pcs. | 2 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Portable Petrol Welding Generator (200А) | pcs. | 2 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Special off-road vehicle with а high-pressure pump | pcs. | 2 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | АІ I-terrain steamer truck | pcs. | 1 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | All-terrain tank truck (volume 10-12 m3) | pcs. | 2 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Lifting unit for well workover with а lifting capacity of 60-80 tonnes. | pcs. | 2 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Cementing unit for repairing wells | pcs. | 3 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Naftogaz | Storage | JSC Ukrtransgaz | Gas turbine gas pumping unit of 25-32 MW | pcs. | 2 | [6 empty] | Provision of natural gas to households, Storage of gas from foreign partners |  |  | no
Ukrhydroenergo | Generation | "Kremenchuk HPP" branch | Compressor Alup 341 No. 2, No. | pcs. | 2 | 208055 | This equipment does not affect the installed capacity | 2 | 6 (2024 year) | 2 month after receiving equipment (2025 year) | Compressors Internetional | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | not procured | yes
Ukrhydroenergo | Generation | "Kremenchuk HPP" branch | Power transformer 250 МВА 347/13,8 кВ | pcs. | 1 | 4288000 | output of 180 MW | 1 | 10 (2025 year) | 3 month after receiving equipment (end of 2025 year) | ASTOR, ZTR, GE | to ensure output of 180 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | Submitted to USAID for procurement | yes
Ukrhydroenergo | Generation | Seredniodniprovska HPP branch | Hydro unit No. 5 (oil head, upper bracket, stator, rotor, winding) | pcs. | 1 | 20000000 | output of 50 MW | 1 | 8 (2025 year) | 20 (2025-2026 year) | UEM, Andritz | to ensure output of 50 MW | To be determined after equipment diagnostics | not procured | yes
Ukrhydroenergo | Generation | Seredniodniprovska HPP branch | Power transformer 130 МВА 150/10,5 кВ | pcs. | 1 | 2144000 | output of 150 MW | 1 | 10 (2025 year) | 3 month after receiving equipment (end of 2025 year) | ASTOR, ZTR, GE | to ensure output of 150 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | Submitted to USAID for procurement | yes
Ukrhydroenergo | Generation | Seredniodniprovska HPP branch | Auxiliary transformer 6,3 МVА 10/6,3 | pcs. | 1 | 184120 | This equipment does not affect the installed capacity | 1 | 6 (2024 year) | 2 after receiving equipment (2025 year) | ASTOR, ZTR, GE | This equipment is necessary to ensure the vital activity of the stations | reserve | not procured | yes
Ukrhydroenergo | Generation | Seredniodniprovska HPP branch | Excitation transformers type ТСРЗ 1690/10,5-0,765 | pcs. | 1 | 107200 | output of 44 MW | 1 | 4 (2024 year) | 1 month after receiving equipment (2024 year) | ASTOR, ZTR, GE | to ensure output of 44 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | Submitted to USAID for procurement | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | Power transformer ТРД-90000/110 Block No.5 | pcs. | 1 | 1483106 | output of 88 MW | 1 | 10 (2025 year) | 3 month after receiving equipment (end of 2025 year) | ASTOR | to ensure output of 88 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | The purchase was funded by an IBRD Loan Agreement No. 9284-UA | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | SF6 block circuit-breaker ВТ-5 GL-312F1 | pcs. | 1 | 216098 | This equipment does not affect the installed capacity | 2 | 6 (2024 year) | 2 month after receiving equipment (2025) | АВВ, ALSTOM |  | This equipment is critically needed for the autumn-winter period 2024-2025 | Submitted to USAID for procurement | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | Transformer disconnector Т-5 three-phase 600А S2DAT | pcs. | 1 | 19645 | This equipment does not affect the installed capacity | 2 | 6 (2024 year) | 2 month after receiving equipment (2025) | АВВ |  | This equipment is critically needed for the autumn-winter period 2024-2025 | Submitted to USAID for procurement | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | Single-phase current transformer IMB 123 Block No.5 | pcs. | 3 | 88404 | This equipment does not affect the installed capacity | 2 | 6 (2024 year) | 2 month after receiving equipment (2025) | АВВ | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | Single-phase current transformer IMB 123 Block No.4 | pcs. | 1 | 29560 | This equipment does not affect the installed capacity | 2 | 6 (2024 year) | 2 month after receiving equipment (2025) | АВВ | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | Power transformer ТРД-90000/110 Block No.4 | pcs. | 1 | 1483106 | output of 88 MW | 1 | 10 (2025 year) | 3 month after receiving equipment (end of 2025 year) | ASTOR | to ensure output of 88 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | The purchase was funded by an IBRD Loan Agreement No. 9284-UA | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | Excitation transformers of Resibloc ТВ-16 – ТВ-21 type | pcs. | 6 | 88385 | output of 132 MW | 1 | 4 (2024 year) | 1 month after receiving equipment (2024 year) | АВВ, ALSTOM | to ensure output of 132 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | Auxiliary transformer 10/0,4 kV 630 kVA Т-15-3, Board 15СО | pcs. | 1 | 98226 | This equipment does not affect the installed capacity | 1 | 4 (2024 year) | 1 month after receiving equipment (2024 year) | ASTOR, ZTR, GE, ABB | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | Power transformer ТРД-90000/110 Block No.6 | pcs. | 1 | 1483106 | reserve | 1 | 10 (2025 year) | 3 month after receiving equipment (end of 2025 year) | ASTOR, ZTR, GE, ABB | equipment in case of the event of an unforeseen emergency situation | reserve | not procured | yes
Ukrhydroenergo | Generation | Kaniv HPP branch | Earthing disconnector ЗОН-110М-ІІ УХЛ1 Block No. 5 | pcs. | 3 | 58936 | This equipment does not affect the installed capacity | 1 | 6 (2024 year) | 2 month after receiving equipment (2025) | АВВ | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Power transfromer ГТ11-12 | pcs. | 1 | 1557692 | output of 224,5 MW | 1 | 6 (2025 year) | 3 month after receiving equipment (end of 2025 year) | ASTOR, ZTR, GE, ABB | to ensure output of 224,5 MW | inspection and repair | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Power transfromer ГТ15-16 | pcs. | 1 | 1557692 | output of 224,5 MW | 1 | 6-10 (2026 year) | 3 month after receiving equipment (2026 year) | ASTOR, ZTR, GE, ABB | to ensure output of 224,5 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Power transfromer ГТ17-18 | pcs. | 1 | 1557692 | output of 224,5 MW | 1 | 6-10 (2026 year) | 3 month after receiving equipment (2026 year) | ASTOR, ZTR, GE, ABB | to ensure output of 224,5 MW | inspection and overhaul | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Power transfromer Т3 | pcs. | 1 | 147339 | This equipment does not affect the installed capacity | 1 | 4-10 (2025 year) | 1 month after receiving equipment (2026 year) | ASTOR, ZTR, GE, ABB | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Power transfromer Т4 | pcs. | 1 | 147339 | This equipment does not affect the installed capacity | 1 | 4-10 (2025 year) | 1 month after receiving equipment (2026 year) | ASTOR, ZTR, GE, ABB | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Circuit-breaker ЕВ ГТ 11-12 | pcs. | 1 | 216098 | output of 224,5 MW | 1 | 6 (2024 year) | 2 month after receiving equipment (2024 year) | АВВ, ALSTOM | to ensure output of 224,5 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Circuit-breaker ЕВ ГТ 15-16 | pcs. | 1 | 216098 | output of 224,5 MW | 2 | 6-10 (2025 year) | 2 month after receiving equipment (2026 year) | АВВ, ALSTOM | to ensure output of 224,5 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Circuit-breaker ЕВ ГТ 17-18 | pcs. | 1 | 216098 | output of 224,5 MW | 3 | 6-10 (2025 year) | 2 month after receiving equipment (2026 year) | АВВ, ALSTOM | to ensure output of 224,5 MW | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Surge arrester ГТ 11-12 | pcs. | 1 | 2946 | This equipment does not affect the installed capacity | 1 | 4 (2024 year) | 1 month after receiving equipment (2024 year) | АВВ, ALSTOM | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | restoration | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Surge arrester ГТ 13-14 | pcs. | 1 | 2946 | This equipment does not affect the installed capacity | 2 | 4 (2024 year) | 1 month after receiving equipment (2024 year) | АВВ, ALSTOM | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Surge arrester ГТ 15-16 | pcs. | 1 | 2946 | This equipment does not affect the installed capacity | 2 | 10 (2025 year) | 1 month after receiving equipment (2026 year) | АВВ, ALSTOM | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Surge arrester ГТ 17-18 | pcs. | 1 | 2946 | This equipment does not affect the installed capacity | 3 | 10 (2025 year) | 1 month after receiving equipment (2026 year) | АВВ, ALSTOM | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Surge arrester Л 1 | pcs. | 1 | 2946 | This equipment does not affect the installed capacity | 1 | 4 (2024 year) | 1 month after receiving equipment (2024 year) | АВВ, ALSTOM | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | restoration | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Surge arrester Л-2 | pcs. | 1 | 2946 | This equipment does not affect the installed capacity | 2 | 4 (2024 year) | 1 month after receiving equipment (2024 year) | АВВ, ALSTOM | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Disconnector Л1-01 | pcs. | 1 | 19654 | This equipment does not affect the installed capacity | 1 | 6 (2024 year) | 2 month after receiving equipment (2024 year) | АВВ, ALSTOM | This equipment is necessary to ensure output to the grid | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Disconnector Л1-02 | pcs. | 1 | 19654 | This equipment does not affect the installed capacity | 2 | 6 (2024 year) | 2 month after receiving equipment (2024 year) | АВВ, ALSTOM | This equipment is necessary to ensure output to the grid | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Disconnector Л2-01 | pcs. | 1 | 19654 | This equipment does not affect the installed capacity | 2 | 6 (2024 year) | 2 month after receiving equipment (2024 year) | АВВ, ALSTOM | This equipment is necessary to ensure output to the grid | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Disconnector Л2-02 | pcs. | 1 | 19654 | This equipment does not affect the installed capacity | 3 | 6 (2024 year) | 2 month after receiving equipment (2024 year) | АВВ, ALSTOM | This equipment is necessary to ensure output to the grid | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Voltage transformer ТН Л1 | pcs. | 1 | 32160 | This equipment does not affect the installed capacity | 1 | 4 (2024 year) | 1 month after receiving equipment (2024 year) | АВВ | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | restoration | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Voltage transformer ТН Л2 | pcs. | 1 | 32160 | This equipment does not affect the installed capacity | 2 | 4 (2024 year) | 1 month after receiving equipment (2024 year) | АВВ | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Current transformer ГТ11-12 | pcs. | 1 | 29467 | This equipment does not affect the installed capacity | 1 | 2-4 (2024 year) | 1 month after receiving equipment (2024 year) | АВВ | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Current transformer ГТ13-14 | pcs. | 1 | 29467 | This equipment does not affect the installed capacity | 2 | 2-4 (2024 year) | 1month after receiving equipment (2024 year) | АВВ | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Current transformer ГТ15-16 | pcs. | 1 | 29467 | This equipment does not affect the installed capacity | 2 | 2-8 (2025 year) | 1 month after receiving equipment (2026 year) | АВВ | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Current transformer ГТ17-18 | pcs. | 1 | 29467 | This equipment does not affect the installed capacity | 3 | 2-8 (2025 year) | 1 month after receiving equipment (2026 year) | АВВ | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Tailrace gate set No.1 | pcs. | 1 | 595588 | This equipment does not affect the installed capacity | 2 | 6 (2025 year) | 2 month after receiving equipment (2025 year) | Ukrsteelconstruction | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | repair | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Tailrace gate set No.2 | pcs. | 1 | 595588 | This equipment does not affect the installed capacity | 2 | 6 (2025 year) | 2 month after receiving equipment (2025 year) | Ukrsteelconstruction | This equipment is necessary to ensure the vital activity of the stations | This equipment is critically needed for the autumn-winter period 2024-2025 | repair | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Semigantry unit crane No.2 | pcs. | 1 | 27000000 | This equipment does not affect the installed capacity | 1 |  |  | Ukrsteelconstruction | This equipment is necessary for the safe operation of the plant |  | Procurement with EBRD, EIB loan funds, Loan Agreement No. 47947 dd. 30.12.2015 | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Semigantry unit crane №1 | pcs. | 1 |  |  | 1 |  |  | Ukrsteelconstruction |  |  | Procurement with EBRD, EIB loan funds, Loan Agreement No. 47947 dd. 30.12.2016 | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Unit cranes runways | pcs. | 1 |  |  | 1 | [5 empty] | Procurement with EBRD, EIB loan funds, Loan Agreement No. 47947 dd. 30.12.2017 | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Unit cranes power trolleys | pcs. | 1 |  |  | 1 | [5 empty] | Procurement with EBRD, EIB loan funds, Loan Agreement No. 47947 dd. 30.12.2018 | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Gantry crane Service bridge НБ ДГЭС-2 | pcs. | 1 |  |  | 1 | [5 empty] | Procurement with EBRD, EIB loan funds, Loan Agreement No. 47947 dd. 30.12.2019 | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Service bridge crane runways | pcs. | 1 |  |  | 1 | [5 empty] | Procurement with EBRD, EIB loan funds, Loan Agreement No. 47947 dd. 30.12.2020 | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Lifting beam for handling a rotor | pcs. | 1 |  |  | 2 |  |  | Ukrsteelconstruction |  |  | Procurement with EBRD, EIB loan funds, Loan Agreement No. 47947 dd. 30.12.2021 | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydraulic turbine with equipment set, № 14 | pcs. | 1 | 30000000 | has been under reconstruction | 2 | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM | output of 120 MW |  | needs to be diagnosed | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydro generator with equipment set No. 14 | pcs. | 1 |  |  |  | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM |  |  | needs to be diagnosed | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydraulic turbine with equipment set, № 17 | pcs. | 1 | 30000000 | output of 120 MW | 3 | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM | output of 120 MW |  | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydro generator with equipment set No. 17 | pcs. | 1 |  |  |  | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM |  |  | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydraulic turbine with equipment set, № 18 | pcs. | 1 | 30000000 | output of 120 MW | 3 | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM | output of 120 MW |  | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydro generator with equipment set No. 18 | pcs. | 1 |  |  |  | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM |  |  | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydro generator with equipment set No. 15 | pcs. | 1 | 17000000 | output of 120 MW | 2 | 16 (2025 year) | 18 month after receiving equipment (2026 year) | UEM | output of 120 MW |  | needs to be diagnosed | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydro generator with equipment set No. 16 | pcs. | 1 | 17000000 | output of 120 MW | 2 | 16 (2025 year) | 18 month after receiving equipment (2026 year) | UEM | output of 120 MW |  | needs to be diagnosed | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | DC panel ВУ1, ВУ2, ВУ3 | pcs. | 1 | 200570 | This equipment does not affect the installed capacity | 1 | 6 (2024 year) | 2 month after receiving equipment (2024 year) | Elektrotexnik Corporation | This equipment is necessary to ensure the vital activity of the stations | This equipment provides direct current to the station | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Truck Crane Liebherr ELTM 1300-6.4 (STANDART) or the analogue is not worse | pcs. | 1 | 1964525 | This equipment does not affect the installed capacity | 3 | 1 (2024 year) | This equipment does not require installation (2024 year) | Liebherr | This equipment is necessary to ensure the vital activity of the stations | Requested through the UESF - support request was approved, the funds were allocated for the procurement. The company informed unoffcicialy, that the item is not needed anymore. Due to the lack of urgency the reservation of funds is to be cancelled under the current Framework Agreement | Procurement with USAID funds | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydraulic turbine with equipment set, № 8 | pcs. | 1 | 30000000 | output of 72MW | 1 | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM | to ensure output of 72MW |  | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydro generator with equipment set No. 8 | pcs. | 1 |  |  | 1 | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM |  |  | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydraulic turbine with equipment set, № 9 | pcs. | 1 | 30000000 | output of 72MW | 1 | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM | to ensure output of 72MW |  | not procured | yes
Ukrhydroenergo | Generation | Dnipro HPP branch | Hydro generator with equipment set No. 9 | pcs. | 1 |  |  | 1 | 18 (2025 year) | 20 month after receiving equipment (2026-2027 year) | UEM |  |  | not procured | yes
Ukrenergo | TSO |  | Autotransformer 330 ATDTSN - 250000/330/150/35 | set (3 phases) | 2 | 5000000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 330 ATDTTN - 250000/330/150/10 | set (3 phases) | 2 | 5000000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 330 ATDTN - 200000/330/110/35 | set (3 phases) | 2 | 4400000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 330 ATDTN - 200000/330/110/10 | set (3 phases) | 2 | 4400000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 330 ATDTN - 200000/330/110/6 | set (3 phases) | 2 | 4400000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 330 ATDTN - 125000/330/110/35 | set (3 phases) | 2 | 3600000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 330 ATDTN - 125000/330/110/10 | set (3 phases) | 2 | 3600000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 330 ATDTN - 125000/330/110/6 | set (3 phases) | 1 | 1800000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 220 ATDTN - 200000/220/110/35 | set (3 phases) | 1 | 2200000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 220 ATDTN - 200000/220/110/10 | set (3 phases) | 1 | 2200000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 220 ATDTN - 125000/220/110/35 | set (3 phases) | 1 | 1800000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 220 ATDTN - 125000/220/110/10 | set (3 phases) | 1 | 1800000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Autotransformer 220 ATDTN - 125000/220/110/6 | set (3 phases) | 1 | 1800000 |  |  | 2025 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Shunt Reactor 750 ROM - 110000/750 | phase | 3 | 3600000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Phase-Shifting Transformer 150 OTDTNP - 92000/150 | phase | 3 | 4500000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; Reserve | Funding agreed | yes
Ukrenergo | TSO |  | Voltage transformer 750 Capacitive Rated Voltage - 750/√3 kV Transformation ratio - 750000/√3/100/√3/100/100/√3 Secondary windings: Accuracy class, Rated voltage, V; Power of windings VA: basic - 0,2; 100/√3; 100 additional - 3Р; 100; 400 basic additional - 0,2; 100/√3;100 | phase | 12 | 480000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Voltage transformer 330 Rated Voltage - 330/√3 kV Transformation ratio - 330000/√3/100/√3/100/100/√3 Secondary windings: Accuracy class, Rated voltage, V; Power of windings VA: basic - 0,2; 100/√3; 200 additional - 3Р; 100; 400 basic additional - 0,5; 100/√3; 200; 1; 100/√3; 300; 3,0; 100/√3; 1200 | phase | 18 | 539694 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Voltage transformer 220 SF6 Rated Voltage - 220/√3 kV Transformation ratio - 220000/√3/100/√3/100/100/√3 Secondary windings: Accuracy class, Rated voltage, V; Power of windings VA: basic - 0,2; 100/√3; 200 additional - 3Р; 100; 400 basic additional - 0,5; 100/√3; 200; 1; 100/√3; 300; 3,0; 100/√3; 1200 | phase | 3 | 35310 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Voltage transformer 150 SF6 Rated Voltage - 150/√3 kV Transformation ratio - 150000/√3/100/√3/100/100/√3 Secondary windings: Accuracy class, Rated voltage, V; Power of windings VA: basic - 0,2; 100/√3; 200 additional - 3Р; 100; 400 basic additional - 0,5; 100/√3; 200; 1; 100/√3; 300; 3,0; 100/√3; 1200 | phase | 21 | 203322 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Voltage transformer 110 SF6 Rated Voltage - 110/√3 kV Transformation ratio - 110000/√3/100/√3/100/100/√3 Secondary windings: Accuracy class, Rated voltage, V; Power of windings VA: basic - 0,2; 100/√3; 200 additional - 3Р; 100; 400 basic additional - 0,5; 100/√3; 200; 1; 100/√3; 300; 3,0; 100/√3; 1200 | phase | 18 | 161136 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Surge arrester 750 Type РВМК-750М Rated Voltage (Ur) - 612 kV Line grade class - 5 | pcs. | 24 | 462840 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Surge arrester 330 Rated Voltage of the SA (Ur) - 288 kV Rated discharge current - 10 kA Line grade class - 3 | pcs. | 54 | 119664 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Surge arrester 220 Rated Voltage of the SA (Ur) - 192 kV Rated discharge current - 10 kA Line grade class - 3 | pcs. | 15 | 26175 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Surge arrester 150 Rated Voltage of the SA (Ur) - 138 kV Rated discharge current - 10 kA Line grade class - 3 | pcs. | 42 | 35515.2 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Surge arrester 110 Rated Voltage of the SA (Ur) - 108 kV Rated discharge current - 10 kA Line grade class - 2 | pcs. | 39 | 25178.4 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | HV bushing 330 Rated current - 1000А | pcs. | 5 | 195000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | HV bushing 150 Rated current - 800А / 1250А / 2000А | pcs. | 12 | 300000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | HV bushing 110 Rated current - 800А / 2000А | pcs. | 30 | 510000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Coupling capacitor 750 Unominal - 750 kV | phase | 2 | 55200 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Coupling capacitor 330 Unominal - 362 kV | phase | 2 | 41400 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Line trap Іnominal - 4000А | pcs. | 1 | 23640 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Battery Battery voltage - 230 V Element voltage - 2 V Capacity - 360 А*h Life span - not less than 20 years | set | 1 | 24600.8 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Terminal cabinet Type ЯЗВ - 90 | pcs. | 10 | 10000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Terminal cabinet Type ЯЗВ - 120 | pcs. | 10 | 11000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Terminal cabinet Type ЯЗВ - 200 | pcs. | 10 | 12000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Control cable KVVGng (kVВГЕнг) 10х2,5 mm2 | m. | 40000 | 140000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Control cable KVVGng (kVВГЕнг) 14х2,5 mm2 | m. | 40000 | 180000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Control cable KVVGng (kVВГЕнг)19х2,5 mm2 | m. | 40000 | 250000 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Gabion Type - MIL 7 | pcs. | 550 | 24750 |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Rail (12.5 m) Р50 | pcs. | 273 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Rail (12.5 m) Р55 | pcs. | 2 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Rail (12.5 m) Р65 | pcs. | 3 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Rail (12.5 m) Р38 | pcs. | 4 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Multi-functional loader According to the specifications | pcs. | 13 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | 6+1 (6 passengers + 1 driver) off-road minibus According to the specifications | pcs. | 1 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Minibus 8+1 According to the specifications | pcs. | 17 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Minibus 16+1 (4х2) According to the specifications | pcs. | 28 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | All-terrain vehicle (4x4) According to the specifications | pcs. | 13 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | mobile drilling rig According to the specifications | pcs. | 1 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Shielding fabric for manufacturing protective suits used for safely performing work on live electrical transmission lines without disconnecting them According to one of the standards: IEC 60895:2002, EN 60895:2003, IEC 60895:2020, or EN IEC 60895:2020 | m2 | 3850 |  |  |  | 4 quarter 2024 |  |  |  | Donor - USAID; | Procurement agreed | yes
Ukrenergo | TSO |  | Circuit Breaker 750 Rated current - 4000А Breaking current of the short-cirucit - 40 кА | set (3 phases) | 8 | 3120000 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Circuit Breaker 420 Rated current - 4000 А Breaking current of the short-cirucit - 40 кА | set (3 phases) | 10 | 1500000 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Circuit Breaker 330 Rated current - 3150А Breaking current of the short-cirucit - 50 кА | set (3 phases) | 1 | 103622 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Circuit Breaker 220 Rated current - 3150 А Breaking current of the short-cirucit - 40 кА | set (3 phases) | 5 | 246310 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Circuit Breaker 150 Rated current - 3150А Breaking current of the short-cirucit - 40 кА | set (3 phases) | 8 | 216968 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Circuit Breaker 110 Rated current - 3150 А Breaking current of the short-cirucit - 40 кА | set (3 phases) | 11 | 247390 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Circuit Breaker 110 Rated current - 2000А Breaking current of the short-cirucit - 50 кА | set (3 phases) | 4 | 89960 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Disconnector 750 kV with one earthing blade 750 Іnominal - 3150А | set (3 phases) | 2 | 313682 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Disconnector 750 kV with two earthing blades 750 Rated current - 3150 А | set (3 phases) | 5 | 784205 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Disconnector 330 kV with one earthing blade 330 Rated current - 3200 (2000)А | set (3 phases) | 1 | 27665 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Disconnector 330 kV with two earthing blades 330 Rated current - 3200 (2000)А | set (3 phases) | 8 | 253858.3 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Disconnector 220 kV with two earthing blades 220 Rated current - 2000А | set (3 phases) | 3 | 87954 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Disconnector 150 kV with one earthing blade 150 Rated current - 2000А | set (3 phases) | 1 | 11364 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Disconnector 150 kV with two earthing blades 150 Rated current - 2000А | set (3 phases) | 10 | 172730 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Disconnector 110 kV with two earthing blades 110 Rated current - 2000А | set (3 phases) | 10 | 80540 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 750 SF6 Transformation ratio - 4000-3000-2000-1500/1 Accuracy class - 0,2S/0,2S/5Р/5Р/5Р/5P | phase | 32 | 2531200 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 330 SF6 Rated voltage - 330 kV Transformation ratio - 1000-2000/1 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 24 | 595440 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 330 SF6 Rated voltage - 330 kV Transformation ratio - 1500-3000/1 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 15 | 372150 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 220 SF6 Rated voltage - 220 kV Transformation ratio - 600-1200/5 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 21 | 503832 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 150 SF6 Rated voltage - 150 kV Transformation ratio - 600-1200/5 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 27 | 376731 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 150 SF6 Rated voltage - 150 kV Transformation ratio - 1000-2000/5 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 15 | 209295 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 150 SF6 Rated voltage - 150 kV Transformation ratio - 1000-2000/1 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 15 | 209295 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 150 SF6 Rated voltage - 150 kV Transformation ratio - 600-1200/1 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 15 | 209295 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 110 SF6 Rated voltage - 110 kV Transformation ratio - 1000-2000/1 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 30 | 379710 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 110 SF6 Rated voltage - 110 kV Transformation ratio - 750-1500/1 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 18 | 227826 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 110 SF6 Rated voltage - 110 kV Transformation ratio - 600-1200/5 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P Rated Secondary Load- 20/20/40/40/40/40 ВА | phase | 18 | 230544 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Current transformers 110 Transformation ratio - 1000-2000/5 Accuracy class - 0,2S/0,2S/10Р/10Р/10Р/10P | phase | 42 | 537936 |  |  | 4 quarter 2024 |  |  |  | Donor - KfW; | Procurement agreed | yes
Ukrenergo | TSO |  | Diesel generators 250 kW | pcs. | 2 | 1350927 |  | 1 | 4 quarter 2024 |  |  |  | Donor - TBD; | Negotiating funding | no | Eastern Region, Substation A Northern Region, Substation B
Ukrenergo | TSO |  | Diesel generators 275 kW | pcs. | 2 |  |  | 1 | 4 quarter 2024 |  |  |  | Donor - TBD; | Negotiating funding | no | Southern Region, Substation C Eastern Region, Substation D
Ukrenergo | TSO |  | Diesel generators 350 kW | pcs. | 6 |  |  | 1 | 4 quarter 2024 |  |  |  | Donor - TBD; | Negotiating funding | no | Southern Region, Substation E Northern Region, Substation F Northern Region, Substation G Western Region, Substation F Western Region, Substation H Western Region, Substation I
Ukrenergo | TSO |  | Diesel generators 400 kW | pcs. | 3 |  |  | 1 | 4 quarter 2024 |  |  |  | Donor - TBD; | Negotiating funding | no | Northern Region, Substation J Northern Region, Substation K Western Region, Substation L
Ukrenergo | TSO |  | Diesel generators 500 kW | pcs. | 1 |  |  | 1 | 4 quarter 2024 |  |  |  | Donor - TBD; | Negotiating funding | no | Northern Region, Substation M
Ukrenergo | TSO |  | Diesel generators 700 kW | pcs. | 3 |  |  | 1 | 4 quarter 2024 |  |  |  | Donor - TBD; | Negotiating funding | no | Northern Region, Substation N Northern Region, Substation O Western Region, Substation P
Ukrenergo | TSO |  | Autotransformer 330 ATDTN - 125000/330/110/6 | set (3 phases) | 2 | 3600000 |  | 1 | 2025 |  |  |  | Donor - TBD; | Negotiating funding | no | Eastern Region, Substation R Eastern Region, Substation R
Ukrenergo | TSO |  | Circuit Breaker 750 Gas-insulated circuit breakers 750 kV type LTB 800E4, U nominal = 800 kV, I nominal = 4000 A, I short-circuit breaking = 40 kA, manufactured by ABB, Sweden | set (3 phases) | 3 | 1170000 |  | 1 | 4 quarter 2024 |  |  |  | Donor - TBD; | Negotiating funding | no | Western region, Substation S Western region, Substation S Western region, Substation S
Ukrenergo | TSO |  | Autotransformer 750 Single-phase 750/330/15.75 kV Autotransformer 333 MVA | phase | 1 | 3600000 |  | 1 | 2025 |  |  |  | Donor - TBD; | Negotiating funding | no | Northern Region, Substation N
Ukrenergo | TSO |  | Phase-Shifting Transformer 150 OTDTNP - 92000/150 | phase | 2 | 3000000 |  | 1 | 4 quarter 2024 |  |  |  | Donor - TBD; | Negotiating funding | no | Eastern region, Substation Q Eastern region, Substation Q
Ukrenergo | TSO |  | Shunt Reactor 750 ROM - 110000/750 | phase | 2 | 2400000 |  | 1 | 4 quarter 2024 |  |  |  | Donor - USAID; | USAID Energy Security Project | yes | Northern Region, Substation N Eastern region, Substation Q
Kremenchuk CHPP | Generation | Department 1 | Jenbacher J920 FleXtra gas piston unit (10,400 MW). (or several containerized gas-piston installations with a total capacity of up to 10 MW, which can be used in clusters of several installations of lower power, with the possibility of parallel connection) | piece | 1 | 6000000 | 10.4 MW | 1 | 01.11.2024 | 01.11.2024 | Jenbacher (or another manufacturer of similar gas piston units) | 10.4 MW of generating capacity. Supply of electricity and heat for 218,000 people, provision of reliable supply of electric power from Krem TPP to the power system and powering of consumers connected to the 6kV generator distribution plant of Krem TPP. | It is proposed to implement the power output of the gas piston plant by connecting it to the existing 6 kV generator distribution plant of the Kremenchuk CHP. It is intended to operate the gas-fired power plant as a stationary unit of continuous generation, but it will also be possible to operate as a shunting power. The mini-gas-fired thermal power plant will be able to produce electricity in parallel with the existing power-generating equipment at the production site of the Kremenchuk Thermal Power Plant, as well as work in an autonomous mode (be a source for generating electricity in a separate power plant). It is necessary to perform the relevant design works. | ESP USAID - in procurement/UESF - in procurement/rubber assistance from Lithuania/or any | yes
Kremenchuk CHPP | Generation | Department 1 | TDTN-63000-150/U1 power transformer | piece | 1 | 850000 | 63 MBA | 1 | 01.02.2025* (taking into account the transformer manufacturing period of 180-210 calendar days) | 01.02.2025* (taking into account the transformer manufacturing period of 180-210 calendar days) | PRIVATE JOINT STOCK COMPANY "ZAPORIZHTRANSFORMATOR" | Supply of electricity and heat for 218,000 people, provision of reliable supply of electric power from Krem TPP to the power system and powering of consumers connected to the 6kV generator distribution plant of Krem TPP. Avoiding the risks of emergency shutdowns of generating equipment and consumers, the possibility of creating repair schemes for planned and preventive repairs of electrical equipment of 6kV and 150kV distribution devices. Fulfillment of the requirements of the State Energy Inspectorate regarding the restoration of the normal scheme of the Krem TPP substation (clause 1 of the separate opinion of the State Energy Inspectorate to the Act on checking the readiness of KREMENCHUTSKA TPP LLC for work in the autumn-winter period of 2023-2024 dated November 3, 2023). | According to the Minutes of the meeting dated 06/21/2024 of the Working Group on the Organization of Humanitarian Aid in the Energy Industry (hereinafter - the Working Group), formed by the order of the Ministry of Energy of Ukraine dated 03/31/2022 No. 142 (as amended), the Working Group decided to approve the equipment under serial number 1 Request for support, according to the letter of KREMENCHUTSKA TETS LLC dated 01.05.2024 No. 01/1645 (power transformer TDTN-63000-150/U1) | UESF reservation of funds confirmed by EnCS ON 18/07/2024. Item is in tender | yes | Block A
Kremenchuk CHPP | Generation | Department 1 | Oil TP-22S TU U23.2-30802090-015:2003, TU U23.2-00149943-544-2004, TU 022409155-98 | t | 32 | 48000 | 105 MW (after the completion of restoration work (overhaul) of turbine unit No. 4, damaged as a result of rocket fire) | 1 | 01.11.2024 | 01.11.2024 | TOB "DIMOIL", "AGRINOL" Company, | 105 MW of generating capacity (after the completion of restoration work (overhaul) of turbine unit No. 4, damaged as a result of rocket fire). Supply of electricity and heat for 218,000 people. Ensuring the technological cycle of thermal and electrical energy production. Restoration of stable operation of the turbine unit No. 4. Avoiding the risks of shutdowns of generating and heating equipment and consumers in the winter period. | Requested through the UESF, the product line item was rejected by the Working Group on the Organization of Humanitarian Aid in the Energy Sector according to the Protocol of its meeting dated 21/06/2024 | ESP USAID - in procurement/rubber assistance from Lithuania/or any | yes
Kremenchuk CHPP | Generation | Department 1 | Pump unit feeding with an electric motor type PE 380-185-5 | sht. | 1 | 151000 | Ensuring the operation of steam generation for the backup of electricity production in the amount of 40 MW | 1 | 01.11.2024 | 01.11.2024 | JSC Sumy Plant Nasosenergomash | Reservation of 40 MW of generating capacity. Supply of electricity and heat for 218,000 people. | Replacement of the feed pump damaged as a result of rocket fire. | ESP USAID - in procurement/UESF - in procurement/rubber assistance from Lithuania/or any | yes
Kremenchuk CHPP | Generation | Department 1 | Mitsubishi Power gas turbine unit, model MOBILEPAC, with an FT8 engine | piece | 1 | 19000000 | 31 MW | 2 | 01.02.2025 | 01.02.2025 | LLC "Mitsubishi Power Aero" (or another manufacturer of similar gas turbine installations) | 31.0 MW of generating capacity, supply of electricity and heat for 218,000 people, provision of reliable supply of electric power from Krem TPP to the power system and power supply to consumers connected to the 6 kV generator distribution unit of Krem TPP. | The introduction of a gas turbine installation is necessary to provide electrical energy to technological equipment in the event of a system accident and a long-term blackout of the power system. The full technological cycle of electrical and thermal energy production on existing equipment will be ensured: - electrical and thermal autonomy of the CHP technological equipment; - the circulation of the coolant in the city of Kremenchuk and the industrial facility with the required temperature in the hydraulic mode, depending on the functioning of the pumping stations of the main heating networks; - supplying water to the heating network in the necessary amount; - provision of heat in the form of technological steam of the main industrial consumer; - supply of electrical energy to the main industrial consumer from GRU-6kV and power supply to the object of housing and communal services in the city of Kremenchuk (KP "KREMENCHUKVODOKANAL"). It is necessary to perform the relevant design works. | ESP USAID - in procurement/UESF - in procurement/rubber assistance from Lithuania/or any | yes
Chernihiv CHPP | CHP | Chernihiv CHPP | Парова турбіна з генератором потужністю 60 МВт | pcs. | 1 | 14000000 | 60/220 MW | 1.1 | 01.10.2024 | 01.10.2027 | Siemens | 136 MW of generating capacity, electricity and heat supply for 70 thousand people | UESF: Support request was approved by MoE on 12.04.2024. Reservation of funds requested by MoE from EnCS | UESF: non-allolcated due to the lack of available funding | no | Block A
Chernihiv CHPP | CHP | Chernihiv CHPP | Реконструкція КЕП «Чернігівська ТЕЦ» із переведенням котлоагрегатів ст. №№1-4 на роботу на вугіллях газової групи | pcs. |  | 14000000 |  | 45292 | 2025 | 2027 |  |  | Виконуються проектні роботи до 12.2024 |  | no | BlockА, BlockВ, BlockС
Chernihiv CHPP | CHP | Chernihiv CHPP | Реконструкція системи збудження Г-2 | pcs. |  | 670000 |  | 45293 | 2025 | 2026 |  |  | Виконуються проектні роботи до 10.2024 |  | no | Block В
Chernihiv CHPP | CHP | Chernihiv CHPP | Заміна екранної системи котлоагрегату ст. №4 | pcs. |  | 870000 |  | 45292 | 01.2025 | 01.06.2025 |  |  | Проектні роботи завершені |  | no | Block А, Block В, Block С
Chernihiv CHPP | CHP | Chernihiv CHPP | Відновлення розпалювальної мазутонасосної | pcs. |  | 570000 |  | 45293 | 2025 | 2026 |  |  | Виконуються проектні роботи до 11.2024 |  | no | Block А, Block В, Block С
Chernihiv CHPP | CHP | Chernihiv CHPP | Проєктні роботи по відновленню мазутного господарства | pcs. |  | 140000 |  | 45293 | 2025 | 2026 |  |  |  |  | no | Block А, Block В, Block С
Chernihiv CHPP | CHP | Chernihiv CHPP | Проєктні роботи по реконструкція ХВО | pcs. |  | 120000 |  | 45293 | 2025 | 2026 |  |  |  |  | no | Block А, Block В, Block С
Chernihiv CHPP | CHP | Chernihiv CHPP | Repair of a turbine generator (Generator TV 60-2) | pcs. |  | 1954031.51 |  | 1 | 2024 | [5 empty] | no | Block А
Kharkiv CHPP 2 | CHP | Thermal power plant "Kharkiv CHPP 2" | Energy boiler of a power plant №10 (67-2СП) | Unit | 1 | 273239.2 | 230 tons/hour | 1 | 15.10.2024 | 30.10.2024 | Ukrainian manufacturer, foreign analogue | plus 45 MW of generating capacity, electricity supply for 36 thousand people |  |  | no | Блок (Котел №10 + Турбіна №5)
Kharkiv CHPP 2 | CHP | Thermal power plant "Kharkiv CHPP 2" | Energy boiler of a power plant №11 (67-2СП) | Unit | 1 | 592318.1 | 230 tons/hour | 1 | 01.08.2024 | 20.10.2024 | Ukrainian manufacturer, foreign analogue | plus 45 MW of generating capacity, electricity supply for 36 thousand people |  |  | no | Блок (Котел №11 + Турбіна №7)
Kharkiv CHPP 2 | CHP | Thermal power plant "Kharkiv CHPP 2" | General station equipment and buildings | Unit | 1 | 628984.7 |  | 1 | 01.08.2024 | 15.11.2024 | Ukrainian manufacturer, foreign analogue |  |  |  | no
Kharkiv CHPP 2 | CHP | Thermal power plant "Kharkiv CHPP 2" | Turbogenerator №7(turbine Т-37/50-90 generator ТВ-50-2) | Unit | 1 | 608977.8 | 50 MW | 1 | 15.11.2024 | 1.3.2025 | Ukrainian Energy Machines, GE, Siemens | plus 45 MW of generating capacity, electricity supply for 36 thousand people |  |  | no | Блок (Котел №11 + Турбіна №7)
Kharkiv CHPP 2 | CHP | Thermal power plant "Kharkiv CHPP 2" | Energy boiler of a power plant №12 (67-2СП) | Unit | 1 | 468266.4 | 230 tons/hour | 1 | 01.03.2025 | 30.05.2025 | Ukrainian manufacturer, foreign analogue | plus 45 MW of generating capacity, electricity supply for 36 thousand people |  |  | no | Резервний Котел. Може працювати як з Турбіню №5 так і з Турбиною №7
КП БМР "БЦТМ" | CHP | Теплоцентраль | Трансформатор зв'язку - ТДН 63000/110 Y/Δ-11, 115+9 х1,78%/6,3 кВ | шт. | 2 | 1660369.23 | 120 МВт (2х60) | 1 | 01.08.2024 | 01.01.2025 | ПрАТ «Запоріжтрансформатор» | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Вимикач 6 кВ вакуумний трьохполюсний на номінальний струм 8000 А Siemens Energy HB3-C | шт. | 2 | 376436.4 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Комплект: Комірка 6кВ (КУ – 10Ц)з трансформатором напруги 6 кВ - 3*Ivs1 6000/ √3, 100/ √3,100/3 0.5P - 6 шт; комірка 6кВ (КУ – 10Ц) з вакуумним вимикачем 6 кВ - 11шт; Комірка 6кВ (КУ – 10Ц) з втичним роз'єднувачем 6кВ - 2 шт. | шт. | 1 | 261553.6 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Акумуляторна батарея разом з підзарядним пристроїм - 16Ogi 880 Сlassic 112 банок | шт. | 2 | 178173.7 | 120 МВт | 1 | 01.08.2024 | 1.1.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Панель основного захисту генератора, панель резервного захисту генератора | шт. | 2 | 91659.5 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Панель основного захисту ПЛ-110 кВ, Панель резервного захисту ПЛ-110 кВ, | шт. | 1 | 81475.1 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Вимірювальні трансформатори струму 110кВ - IOSK 123 1000/5А, 0,2S/0,2 S /10Р/10Р/10Р | шт. | 12 | 67911.3 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Реактор заземлюючий дугогасний 6 кВ з плавним регулюваннямРЗДПОМ (А)-300/6 У1 | шт. | 2 | 44363.8 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Панель основного захисту тр-ра зв'язку, панель резервного захисту тр-ра зв'язку | шт. | 2 | 44047.5 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Лінійні роз'єднувачі 110 кВ - ONIII-126/2500/U2 | шт. | 2 | 35998.7 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Реактор заземлюючий дугогасний 6 кВ з ступінчатим регулюваннямРЗДСОМ (А)-480/6 У1 | шт. | 2 | 34719.5 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Панель регулювання дугогасних котушок 6 кВ, Панель регулювання дугогасної котушки ; | шт. | 1 | 15267.6 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Панель реле центральної сигналізації | шт. | 1 | 13897.5 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Панель центральних апаратів синхронізації, панель синхронізації | шт. | 1 | 12093.9 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Прохідні ізолятори - ИП-10/10000-42,5 УХЛ1 | шт. | 12 | 11096.9 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Трансформатор силовий 6/0,4 кВ, 400 кВА, Ун/Д-11 з ПБВ ±2x2,5% ТМ 400/6 У1 | шт. | 2 | 10415.9 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Ізолятор опорно-стержневий 35 кВ,ОНШ-35-20 УХЛ1 | шт. | 96 | 9777 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Панель лічильників | шт. | 2 | 9165.9 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Панель захисту струмопровода 6 кВ | шт. | 2 | 7850.4 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Обмежувачі перенапруг 110 кВ - SBKC 108/SM-II | шт. | 2 | 4514.3 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Трансформатори напруги 6 кВ - Ivs1 6000/ √3, 100/ √3,100/3 0.5P (група з трьох трансформаторів) | шт. | 4 | 10415.8 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб | UESF - Support request was approved by MoE on 05/07/2024. The reservation of funds was requested, not confirmed by EnCS | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no
КП БМР "БЦТМ" | CHP | Теплоцентраль | Шина алюмінієва коробчатого ГОСТ 13623-90 перерізу АТ-200х90х12 | м | 152 | 353.2 | 120 МВт | 1 | 01.08.2024 | 01.01.2025 |  | 120 МВТ для виробництва електроенергії та тепла для 60 тисяч осіб |  | Розміщено потребу на платформах AID ENERGY, ENERGY COMMUNITY | no